THE ANNUAL

ADMINISTRATIVE REPORT

for

AHAFO ANO NORTH MUNICIPAL ASSEMBLY

YEAR 2022

AHAFO ANO NORTH MUNICIPAL ASSEMBLY P. O. Box 70 Tepa - Ashanti

In case of reply the number and date of this letter should be quoted

Our Ref:.................................................................................

Your Ref:...............................................................................

Date………………………………………………………

SUMISSION OF 2022  ANNUAL ADMINISTRATIVE REPORT

I submit herewith, the 2022 Annual Administrative Report for the Ahafo Ano North Municipal Assembly for your kind attention and necessary action, please.

Thank you.

ABDUL-HUSSEIN A. RASHEED

(AG. MUNICIPAL CO-ORD. DIRECTOR)

FOR: MUNICIPAL CHIEF EXECUTIVE

THE HON. REGIONAL MINISTER

ASHANTI REGIONAL CO-ORD. COUNCIL (ARCC)

KUMASI- ASHANTI

Tel: +233-3220-20044/20046

Email:admin@aanma.gov.gh

ASHANTI REGION    	 Info@aanma.gov.gh

Website: www.aanma.gov.gh

# TABLE OF CONTENTS

TABLE OF CONTENTS	i

1.0 EXECUTIVE SUMMARY	1

2.0 INTRODUCTION	2

2.1 Report Review Period	2

2.2 Profile of the Municipal	2

2.3 Mission Statement	2

2.4 Vision	2

2.5 Political Description	2

2.6 Location and Size	3

2.7 Relief and Drainage	3

2.8 Climate	4

2.9 Vegetation	4

2.10 Topography	4

2.11 Drainage	4

3.0 ADMINISTRATIVE ISSUES	5

3.1 Departments, Agencies & Services	5

3.2 Political Leadership of MMDA	6

3.2.1. Department Integration	6

3.3 Recruitment, Upgrading, Promotions, Postings, and Transfers	7

3.4 Competency-Based Training Undertaken In 2022(Institution-Specific)	9

3.5 Staff List (As At 01-Dec-2022)	11

3.6 Composite Budget Issues	19

3.7 Security Issues in the Municipality	19

3.9 38 th National Farmers Day Celebration.	19

4.0 REPORTS FROM THE DEPARTMENTS OF THE ASSEMBLY	21

4.1 DEPARTMENT OF SOCIAL WELFARE AND COMMUNITY DEVELOPMENT	21

4.1.1 Justice Administration:	21

4.1.2 Child Right Promotion and Protection:	21

4.1.3 Community Care:	23

4.1.4. Mass Education	24

4.2	GHANA EDUCATION SERVICE	26

4.2.1	Key Activities Identified For Performance	26

4.2.2. Basic Education:	26

4.3 NATIONAL HEALTH INSURANCE SCHEME (NHIS)	32

4.3.1 Registration	32

4.3.3 Innovative Programme	32

4.4. GHANA NATIONAL FIRE SERVICE	33

4.4.1. Activities Carried Out During the Year	33

4.5 PHYSICAL PLANNING DEPARTMENT (PPD)	34

4.5.1 Development Control Measures	34

4.5.2. Street Naming and Property Addressing	39

4.5.3. Spatial Plans Preparation	40

4.5.4	Ghana Secondary City Support Programme (GSCSP)	41

4.6. GHANA POLICE SERVICE	42

4.6.1. Organization and Police Activities:	42

4.6.1.1.	42

4.7	DEPARTMENT OF AGRICULTURE	44

4.7.1 Districts Activity Implementation Efficiency Ratio	44

Child labour prevention and Safety protocols on COVID-19 etc.	45

4.8	BUSINESS ADVISORY CENTRE	59

4.8.1. Activities Planned for the Year	59

4.8.2	Activities Implemented for the Year	61

4.9	GHANA AMBULANCE SERVICE	68

4.9.1. Emergencies attended within the Year 2022	68

4.9.2	Distribution of Cases attended under Age And Sex	69

4.9.3	Classification of Cases by Chief Complain / Type Of Illness	70

4.9.4	Cases Referred from Tepa Municipal Hospital to Sunyani Regional Hospital, Komfo Anokye Teaching Hospital (Kath) and Other Facility	72

4.9.5	Names of Health Centers and Chip Compound Cases Transported within the Municipality	72

4.9.6	Cases Referred Outside Tepa Municipality To Other Receiving Facility	72

4.10 NATIONAL DISASTER MANAGEMENT ORGANIZATION (NADMO)	74

4.10.1. Programmes & Project	74

4.10.2	Pre-Disaster Management Activities	74

4.10.3	Disaster Risk Reduction and Climate Change Adaption	75

4.11 National Commission For Civic Education (NCCE)	76

4.11.1. General Overview of Activities Undertaken	76

4.11.2	Assessment of the Activities	79

4.12	ENVIRONMENTAL HEALTH UNIT	81

4.12.1 Activities Carried Out	81

5.0 APPENDIXES	86

5.1 Summary of Development Projects-Appendix I	86

5.2 Project List-Appendix 2	87

5.3 Financial Performance 2022–Ahafo Ano North Municipal Assembly-Appendix 3	89

5.3.1. Revenue Mobilization – Appendix 4	90

5.3.2 Expenditure – Appendix 5	91

5.4 Variance of Financial Performance- Appendix 6	92

5.5 Way Forward	92

# 1.0 EXECUTIVE SUMMARY

The 2022 Annual Performance Report provides a general overview of the implementation of the policies and programmes of both the Central Government and the Municipal Assembly in the Ahafo Ano North Municipal.

The report covers substantial programmes and activities as outlined or prioritized and implemented in the Annual Action Plan of the Municipal Assembly. The report highlights the general profile of the Assembly -Pits mission, organizational structure, functions, and the activities of the various departments.

The membership of the Assembly is fifty-eight (58) comprising of thirty-nine (39) elected representatives, seventeen (17) government appointees, MCE and MP. However, the MP does not have a voting right.

Out of the thirteen (13), decentralized departments prescribed by the L. I. 1961 for the Municipal Assembly, twelve (12) are well established and fully integrated. However, Transport Department is non-existent.

The Assembly's IGF performance as of the end of December 2022 was GHC 635,502.70 out of the total estimate of GHC848,000.00 representing 74.94%. The Assembly expenditure also stood at GHC 693,942.05 representing 83.48%.

As of the end of the year, the Assembly had received the first, second, third and fourth quarter of 2022 DACF amounting to a total sum of GHC 1,615,948.65. This development impacted positively on the progress of work on projects.

The summary of developmental projects undertaken in the year was fourteen (14) projects of which four (4) have been completed and the remaining ongoing.

The thrust areas for the Assembly in the ensuing year include;

- Increase in revenue mobilization.

- Continuous Implementation of government flagship project.

-complete ongoing projects

-Build capacity of staff

# 2.0 INTRODUCTION

## 2.1 Report Review Period

This report covers activities undertaken by the Ahafo Ano North Municipal Assembly between the periods of 1st January – 31st December 2022. It highlights issues on governance, economy, social, infrastructure, security, and a summary of reports from the other departments.

## 2.2 Profile of the Municipal

The Ahafo Ano North Municipal Assembly was then established in 1988 by Legislative Instrument L.I. 1402 as a District.  The Assembly attain its Municipal status in 2018 with a Legislative Instrument L. I 2264.

The Municipality is located in the northwestern part of the Ashanti Region with Tepa as the Municipal capital. It shares boundaries with five (5) Districts, namely; Tano North and South to the North; Asutifi South to the West, all in the Ahafo Region and to the South by Atwima Mponua; and to the East by Ahafo Ano South East and Ahafo Ano South West, also in the Ashanti Region. It has a land area of 576 km2 (0537 ha) with a population of 94,285 (2010 Population and Housing Census). The Population is made up of 47,956 Ms and 46,329 Fs.  Other major towns in the Municipality are Manfo, Mabang, Akwasiase, Anyinasuso, Asuhyiae, and Subriso.

## 2.3 Mission Statement

The Ahafo Ano North Municipality exists to improve the living conditions of the people of the Municipal by mobilizing the human and material resources in providing social and infrastructure facilities and services.

## 2.4 Vision

To provide the basic and balanced needs of its people.

## 2.5 Political Description

The Assembly has a membership of fifty-eight (58) made up of thirty-nine (39) elected members representing the same number of electoral areas in the District and seventeen (17) Government Appointees. The Hon. Municipal Chief Executive and the Hon. Member of Parliament for Ahafo Ano North Constituency are also members of the Assembly. However, the Hon. Member of Parliament has no voting right in the Assembly.

The Assembly operates through the Committee System. At the apex of the Committees is the Executive Committee chaired by the Municipal Chief Executive. Beneath the Executive Committee are the five (5) statutory sub-committees, namely Social Services; Development Planning: Works; Justice and Security; and Finance and Administration. There are other two (2) adho Sub-Committee namely Agric and Gender. Membership of the Executive is made up of chairpersons of the sub-committees, the chairperson of one ad hoc Sub-Committee of the Executive Committee elected by the Municipal Assembly, and any two other members elected by members of the Municipal Assembly, at least one of whom is a woman.

The Municipality is divided into 7 sub-structures for administrative conveniency. These sub-structures are made up of one Town Council and six Zonal Councils, namely; Tepa Town Council and Anyinasuso, Subriso, Biakoye, Kwasu Abu, Abu Bone, and Suponso Area Councils. Also, there are thirty-nine (39) Unit Committees with one hundred and ninety-five (195) Unit Committee Members.

## 2.6 Location and Size

The Ahafo Ano North Municipality is located between latitude 6 47’N and 7 02’N and longitude 2 26’W and 2 04’W.  It shares boundaries with three districts, i.e. Tano North and South, Asutifi South, Atwima Mponua, and Ahafo Ano South Districts. Many traders from these areas converge at Tepa weekly market to sell their goods due to its geographical position and in turn buy local staples like plantain, cassava, maize, vegetables, etc. in large quantities.

## 2.7 Relief and Drainage

The Municipality is located on the forest dissected plateau with Pre-Cambrian rocks of the Birimean formation that underlie this physiographic region.  It rises from about 700 feet in the western part to about 900 feet above sea level.  The area is characterized by a gently rolling landscape drained by many rivers.  The major river in the entire Municipality is the river Tano, which exhibits a dendritic pattern of flow.  The river Anyinasuso, a major tributary of Tano, flows from the east to the west.  It must be emphasised that the river Tano contains enough water, which can be dammed for irrigation farming and to generate hydroelectric power.

## 2.8 Climate

The Ahafo Ano North Municipality lies within the wet semi-equatorial zone marked by double maxima rainfall in June and October with a mean annual rainfall of 175cm.  Temperatures are fairly high with a range between 26 C in August and 30 C in March.  The fair temperature and rainfall favour the cultivation of cocoa and many food crops. The Municipality enjoys bi-modal rainfall and therefore the farmers, mostly old people above forty years undertake serious farming both in the major and minor seasons since farming is mainly rain-fed.

## 2.9 Vegetation

The vegetation of the area is mostly moist deciduous forest, which does not differ much from the rainforest.  Most of the trees shed their leaves during the dry season but not at the same time.  Some economic trees found in the area are the Sapele, Odum, Wawa, and Mahogany.  Human activities of lumbering and farming are drastically reducing the virgin forest to a secondary one with pockets of grasses found at various places.  Sugar cane thrives very well in the lowland areas of the Tano River and some of the other rivers.

## 2.10 Topography

The Municipality exhibits gradually rise from 17.8m in the western part to about 22.86m above sea level.  The land area is very undulating subjecting it to erosion and therefore lowering the productivity of the land.

## 2.11 Drainage

Major rivers and streams include the Tano, Abu, Kwasu, Anyinasuso, and Suponso.  Broad flat banks can be found along with Tano, Kwasu, and Abu.  Tano and its tributaries converging at Asuhyiae place it on a high tourist potential. Most of the streams in the MUNICIPAL dry up during the dry season making them impossible to be used for irrigation.

# 3.0 ADMINISTRATIVE ISSUES

## 3.1 Departments, Agencies & Services

As promulgated by the L. I 1961, the Assembly has thirteen (13) departments. Of the thirteen departments prescribed, the Ahafo Ano Municipal does not have Transport Department. However, the Assembly has eleven (12) of them well established. They include;

1)	Central Administration

2)	Department of Food and Agriculture

3)	Department of Social Welfare and Community Development

4)	Health Department

5)	Department of Physical Planning

6)	Department of Education, Youth, and Sport

7)	Finance Department

8)	Disaster Prevention and Management Department

9)	Department of Trade and Industry

10)	Works Department

11)	Natural Resources Conservation Department

12)	Department Urban Roads

SUBVENTED AGENCIES

1)	National Commission for Civic Education (NCCE)

2)	Committee for Human Rights and Administrative Justice (CHRAJ)

3)	Electoral Commission (EC)

4)	National Health Insurance

5)	National Youth Council

6)	Ghana Water Company Limited

7)	Nation Builders Corps

8)	Volta River Authority

9)	Center for National Culture

10)	Traditional Council

SERVICES

1)	Ghana Police Service

2)	Ghana Fire Service

3)	Ghana Audit Service

4)	Information Service

6)	Judicial Service

7)	Ghana Postal Service

8)	Immigration Service

9)	National Investigation Bureau

10)	National Ambulance Service

## 3.2 Political Leadership of MMDA

The Ahafo Ano Municipal Assembly is made up of fifty-eight (58) members, comprising thirty-nine (39) elected, seventeen (17) Government Appointees, the Member of Parliament who has no voting rights and the District Chief Executive who is both the administrative and political head of the district. The Assembly members are made up of seven (7) Females and fifty (51) Males.

| NAME OF MMDA | NAME OF MMDCE | ASSEMBLY MEMBERS |  |  |
| --- | --- | --- | --- | --- |
|  |  | M | F | TOTAL |
| Ahafo Ano North Assembly | Hon. Martina Appiah-Nyantakyi | 51 | 7 | 58 |

### 3.2.1. Department Integration

As promulgated by the L. I 1961, the Assembly has thirteen departments. Of the thirteen departments prescribed, the Ahofo Ano Municipal has eleven (12) of them well established, fully integrated, and report to the District Co-ordinating Director. They include; Central Administration, Department of Food and Agriculture, Department of Social Welfare and Community Development, Health Department, Department of Physical Planning, Department of Education, Youth and Sport, Finance Department, Disaster Prevention and Management Department, Department of Trade and Industry, Works Department, Department of Urban Roads and Natural Resource Conservation Department.

| MMDA | NO. OF DEPARTMENTS AVAILABLE | DEPARTMENTS ABSENT | REMARKS |
| --- | --- | --- | --- |
| Ahafo Ano Municipal Assembly | 12 | 1 | There is the non-existence of transport department. The rest of the 12 departments have been effective and have an office space. |

## 3.3 Recruitment, Upgrading, Promotions, Postings, and Transfers

| S/N | NAME | RANK | PREVIOUS STATION | NEW POSTING |
| --- | --- | --- | --- | --- |
|  | AUGUSTINE PEPRAH | CO-ORDINATING DIRECTOR | AHAFO ANO NORTH MUN | TANO SOUTH |
|  | SOLOMON DADSON | ASSISTANT DIRECTOR I | AHAFO ANO NORTH MUN | OFFINSO NORTHA |
|  | ALBENT KWAME BOATENG | ASST. DIRECTOR, SOCIAL WALFARE | AHAFO ANO NORTH MUN | K. M.A |
|  | SOLOMON AGYEKUM KENNY | ASST. PUBLIC HEALTH ENGINEER | AHAFO ANO NORTH MUN | AHAFO ANO NORTH EAST |
|  | EBENEZER KOJO QUARM | SNR. DEV’T PLANNING OFFICER | AHAFO ANO NORTH MUN | AFIGYA KWABRE |
|  | GEORGE BOAKYE | ASST. CHIEF ENV’TAL HEALTH OFFICER | AHAFO ANO NORTH MUN | ATWIMA KWAWOMA |
| 1. | OWUSU KWARTENG | ASST. INTERNAL AUDITOR TRAINEE | ATWIMA NWABIAGYE NORTH | AHAFO ANO NORTH MUN |
| 2. | JAMON FEIGBEN | SNR. DEVELOPMENT PLANNING OFFICER | AFIGYA KWABRE | AHAFO ANO NORTH MUN |
| 3. | GYABAA KYEREMEH | PRIN. REVENUE SUPRETENDENT | AFIGYA KWABRE | AHAFO ANO NORTH MUN |
|  | CYNTHIA KYEI | ASST. INTERNAL AUDITOR | AHAFO ANO SOUTH EAST | AHAFO ANO NORTH MUN |
|  | MICHAEL FRIMPONG | SNR. INTERNAL AUDITOR | ASOKORE MAMPONG | AHAFO ANO NORTH MUN |
| 4. | FRANCIS YANZU ALEX | ENGINEER | SEKYERE SOUTH | AHAFO ANO NORTH MUN |
| 5. | JOSEPH BOATENG | ASSISTANT DIRECTOR IIB | RCC | AHAFO ANO NORTH MUN |
|  | ARAFAT ABDULAI | ASST. DEV’T PLANNING OFFICER | RCC | AHAFO ANO NORTH MUN |
|  | NASIBATU SAFIANU MANKAH | ASST. BUDGET ANALYST | RCC | AHAFO ANO NORTH MUN |
|  | ABIGAIL AMPONSAH | ASST.INTERNAL AUDITOR | RCC | AHAFO ANO NORTH MUN |
|  | ARMAH FAROUK | ASST. ENGINEAR | RCC |  |
|  | FRANCIS ANTOA MENSAH | SNR. EXECUTIVE OFFICER | RCC | AHAFO ANO NORTH MUN |
|  | CHARLES AZUMAH BABA | SNR. GARDENER | RCC |  |
|  | OSEI KWADWO | TECHNICAL ASSISTANCE | RCC | AHAFO ANO NORTH MUN |
|  | AWUAH DORMAH DANSO DENIEL | TECHNICAL ASSISTANCE | RCC | AHAFO ANO NORTH MUN |
|  | CHARLES AKPARIBO | ENVIRONMENTAL HEALH ASSISTANCE | RCC | AHAFO ANO NORTH MUN |
|  | RONALD BONSU OPOKU | ASST. ENV’TAL HEALTH ANALYST | RCC | AHAFO ANO NORTH MUN |
|  | PRINCE AKUOKU | DRIVER GDIII | RCC | AHAFO ANO NORTH MUN |
|  | NICHOLAS SOSU | DRIVER GDIII | RCC | AHAFO ANO NORTH MUN |
|  | SAMMUEL ADJEI | DRIVER GDIII | RCC |  |
|  | MARY DARKWA | LABOURER | RCC | AHAFO ANO NORTH MUN |
|  | JOYCE AMANIN | LABOURER | RCC | AHAFO ANO NORTH MUN |
|  | EMMANUEL BOADI | ASST. SECURITY OFFICER | RCC | AHAFO ANO NORTH MUN |
|  | TANIMU MOHAMMED | ASST. SECURITY OFFICER | RCC | AHAFO ANO NORTH MUN |

During the year under review, twenty-four (24) officers were posted to the Municipality and six (6) officers posted out of the Municipality.

PROMOTIONS (2022)-TABLE 4

| S/N | NAME | PREVIOUS RANK | PROMOTED TO | EFFECTIVE DATE |
| --- | --- | --- | --- | --- |
| 1. | ISAAC FRIMPONG | SOCIAL DEVELOPMENT OFFICER | SNR. SOCIAL DEVELOPMENT OFFICER | 01-06-2022 |
| 2. | MANU GODSON | SNR. TECHNICAL OFFICER | PRIN. TECHNICAL OFFICER |  |
| 3. | ISSAH IBRAHIM | ASST. SECURITY GUARD | SECURITY GUARD | 01-06-2022 |
| 4. | ABUBAKAR ALIDU | ASST. SECURITY GUARD | SECURITY GUARD | 01-06-2022 |
| 5. | ALHASSAN ABDUL RAHMAN | ASST. SECURITY GUARD | SECURITY GUARD | 01-06-2022 |
| 6. | SETH BOAMAH | ASST. PROCUREMENT OFFICER | PROCUREMENT OFFICER | 01-10-2022 |
| 7 | SANI SIBA | ASST. HUMAN RESOURCE MANAGER | HUMAN RESOURCE MANAGER | 01-10-2022 |
| 8 | GODSON MANU | TECHNICAL OFFICER | SNR. TECHNICAL OFFICER | 01-10-2022 |

Based on approval from the Local Government Service Secretariat qualified employees from the under listed classes were promoted within the year. The table above shows the details.

## 3.4 Competency-Based Training Undertaken In 2022(Institution-Specific)

There was competency-based training undertaken for staff during the period under review. The training programmes are listed below;

- A day workshop on Pre-Launch of 2021 Leaque Table & Dissemination of 2020 District Leaque Table for MPO, MCD, DIRECTOR- SW/CD on 28/04/2022.

- Two (2) day workshop on Sustaining MAG gains and Local Economic Development-Led for MCE, MCD, MPO, MFO, Head-BAC, Director of Agric on 11-12/04/2022.

- Two (2) day Ghana Secondary Cities Support Programme- GSCSP for MCE, MCD, MPO, MWE on 29-30/04/2022.

- A day training on Revised Composite Budget for Budget Officers on 05/05/2022

- A day training on Dissemination of 2021 Third Quarter Monitoring Report & 2021 Monitoring Exercise on the Land Use and Spatial Planning Authority in the Ashati Region for MCE, MCD, MPO, HRM & PHYSICAL PLANNING OFFICERS on 31/05/2022.

- One (1) day Excel Training for HRM on 30/06/2022.

- A day workshop on women in local leadership, 2022 for Assembly Women on 08/08/2022

- A day workshop on Second Phase of Ghana Productive Safety Net Project (GPSNP2) for MCE, MCD, MPO, MFO, HOD, MWE, D.SW/CD,MWE, DIRECTOR SW/CD, BAC on 19/07/22

- A day training on Capacity Building on Basic Driving Skills& Precautions for Drivers on 23/08/2022.

- A day sensitization training for Operators of the Community Information Centers for Owners of Community Information Centers on 27/07/2022.

- Twelve (12) day workshop on Ghana Electronic Procurement System (GHANEPS) for Procurement Officers, MWE, Auditor, MPO, Supplier & Contractor on 29/08/2022 to 09/09/2022.

- Two (2) day Workshop on 2022 Revised Budget & Uploading on GIFMIS for Budget Officers on 22-23/8 2022.

- A day Orientation on Bye-Laws to provide clarification on the laws used in the draft bye-laws for Assembly members on 02/09/2022.

- A day Workshop on Occupation/Workplace Health and Safety issues at the workplace for MCD, HR on 22/09/2022.

- Two (2) day workshop on Submission of Nominal Roll Data of Staff on GOG payroll system for HR, Accountant & Internal Audit on 06/10/22.

- A day workshop on Records Management, Manual & Fixed Asset Management Tool for Local Government Service for MCE & MCD on 04/11/2022.

- A day workshop on Next Generation Leadership for Hon. Assembly Members on 17/11/2022.

- Five (5) Orientation Programme for Local Government Service Officers for Newly Recruited Staff on 21-25/11/2022.

- A day workshop on Draft National Slum Upgrading & Prevention Strategy for Physical Planning Officer on 25/11/2022.

- A day Workshop on Internal Auditing Policies, Procedures and Roles in MMDAs on 01/12/2022.

AHAFO ANO NORTH MUNICIPAL ASSEMBLY, TEPA-ASHANTI

## 3.5 Staff List (As At 01-Dec-2022)

TABLE 6

| AHAFO ANO- NORTH MUNICIPAL ASSEMBLY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NOMINAL ROLL AS AT DECEMBER,2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. | Name | Sex | Job Grade | Job Class | Staff ID | SSNIT |  | DOB |  | App. Date |  | Mobile Phone |  | Last Prom. |  |
| ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Abdul Hussein A. Rasheed | M | Deputy Director | Coordinating Dir. | 129662 |  | H087008260016 |  | 26/08/1970 |  | 05/02/2006 |  | 547920167 |  | 01/06/2016 |
| 2 | Emmanuel Agyare Sampong | M | Asst Director I | Administration | 912317 |  | E178704260016 |  | 26-Apr-87 |  | 01/11/2012 |  | 246601324 |  | 01/04/2021 |
| 3 | Delali Sylvanus Kwasi | M | Asst. Director IIB | Administration | 1228376 |  | F019205240172 |  | 24-May-92 |  | 01/10/2016 |  | 0248600441 |  |  |
| 4 | Menunatu Amadu | F | Asst. Director IIB | Administration | 907822 |  | F218703100021 |  | 10-Mar-87 |  | 01/11/2012 |  | 244196385 |  | 06/01/2019 |
| 5 | Atta Amponsah | M | Asst. Director IIB | Administration | 1333329 |  | F109102220050 |  | 22-Feb-91 |  | 13/08/2019 |  | 240446737 |  | - |
| 6 | Ferdinand Amponsa Ohene | M | Asst. Director IIB | Administration | 1426125 |  | F019405260191 |  | 26-May-94 |  | 26/10/2020 |  | 540641662 |  | - |
| 7 | Simon Osarfo | M | Asst. Director IIB | Administration | 1332378 |  | E179006060017 |  | 06-Jun-90 |  | 14-08-19 |  | 540829433 |  | - |
| 8 | Afua Ampatatwum Boakye | F | Asst. Director IIB | Administration | 814480 |  | F128208060028 |  | 06/08/1982 |  | 16/11/2020 |  | 244145924 |  |  |
| 9 | Joseph Boateng | M | Asst. Director IIB | Administration | 1328946 |  | F097707010018 |  | 01/07/1977 |  | 02/10/2019 |  | 546487048 |  |  |
| HUMAN RESOURCE DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Sani Siba | M | Asst. Human Resource manager | Human resource | 891190 | F017909250178 |  | 25-Sep-79 |  | 12/06/2012 |  | 244063239 |  |  |  |
| 11 | Hannah Quainoo | F | Asst. Human Resource manager | Human resource | 920251 | B118805200023 |  | 20-May-88 |  | 01/11/2012 |  | 242964048 |  |  |  |
| BUDGET UNIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Boateng Samuel Adjei | M | Snr.Budget Analyst | Budget | 858954 | F378303300015 |  | 30-Mar-83 |  | 01/08/2011 |  | 0208326796 |  | 01/08/2019 |  |
| 13 | Frederick Adu Gyasi | M | Asst. Budget Analyst | Budget | 1415336 | G097902070010 |  | 07/02/1979 |  | 28/10/2020 |  | 243931437 |  | - |  |
| 14 | Frederick Ampontuah | M | Asst. Budget Analyst | Budget | 1332909 | F109010210039 |  | 21/10/1990 |  | 15/07/2019 |  | 542767430 |  | - |  |
| 15 | Nasibatu Mankah Safianu | F | Asst. Budget Analyst | Budget | 1518561 | B0120134708 |  | 01/04/1989 |  | 27/10/2021 |  | 247043502 |  |  |  |
| 16 | Linda Yeboah Apau | F | Asst. Budget Analyst | Budget | 1536245 | G019307150047 |  | 15/07/1993 |  | 27/10/2021 |  | 553299104 |  |  |  |
| INTERNAL AUDIT UNIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 | Micheal Frimpong | M | Snr.Internal Auditor | Audit | 935644 | F019007200152 |  | 20/07/1990 |  | 01/11/2012 |  | 503379157 |  |  |  |
| 18 | Cynthia Kyei | F | Asst.Internal Auditor | Audit | 1333263 | F018809150429 |  | 15/09/1988 |  | 15/10/2019 |  | 557156996 |  |  |  |
| 19 | Frank Tsede | M | Asst. Internal Auditor | Audit | 1405168 | G028103030018 |  | 01-Mar-81 |  | 07/10/2020 |  | 548089235 |  | - |  |
| 20 | Abigail Amponsah | F | Asst. Internal Auditor | Audit | 1518555 | G059010300047 |  | 30-Oct-91 |  | 27/10/2021 |  | 246816972 |  |  |  |
| 21 | Owusu Kwarteng | M | Asst. Internal Auditor Training | Audit | 13332686 | F018707020156 |  | 02-Jul-87 |  | 31/10/2019 |  | 246765496 |  | - |  |
| PLANNING UNIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22 | Jamon Feigbon | M | Snr. Dev't Planning Off. | Planning | 913978 | J056908230019 |  | 23-Aug-69 |  | 18/01/2013 |  | 243454818 |  |  |  |
| 23 | Wilfred Boadu | M | Assist.Planning Officer | Planning | 1330320 | C018909110879 |  | 11/09/1989 |  | 03/01/2020 |  | 244596338 |  | - |  |
| 24 | Arafat Abdulai | M | Assist.Planning Officer | Planning | 1537386 | F219408020032 |  | 02/08/1995 |  | 20/01/2022 |  | 249345391 |  |  |  |
| EXECUTIVE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 25 | Francis Antoa Mensah | M | Snr.Exexuctive Officer | Executive | 1535933 | F088510080012 |  | 08/10/1985 |  | 27/10/2021 |  | 244921995 |  |  |  |
| RECORDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 26 | Talanta Michael | M | Snr. Records Asst. | Records | 69270 | F087803280010 |  | 28-Mar-78 |  | 14/12/2000 |  | 0261200857 |  |  |  |
| 27 | Boakye-Agyemang Winifred | F | Prin. Records Supervisor | Records | 73402 | F087603070027 |  | 07-Mar-76 |  | 01/01/1999 |  | 0243287949 |  | 09/01/2017 |  |
| 28 | Amoako Simon Kofi | M | Snr.Records Supervisor | Records | 19653 | G296811020013 |  | 02-Nov-68 |  | 01/09/1988 |  | 0277165985/050808187 |  | 09/01/2017 |  |
| SECRETARIAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 29 | Antwi Anna Attaa | F | Stenographer Secretary | Secretarial | 774775 | F018201220103 |  | 22-Jan-82 |  | 01/10/2010 |  | 0543639195 |  | 01/10/2017 |  |
| 30 | Emelia Agyapomaa | F | Stenographer Secretary Gd II | Secretarial | 1539374 | F088509200028 |  | 20-Sep-85 |  | 01/06/2022 |  | 243832679 |  |  |  |
| AUXILIARY/SECURITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31 | Abdul-Rahmana Alhassan | M | Assist.Security Guard | Security | 73390 | H016307012377 |  | 16-Jul-64 |  | 01/01/1999 |  | 0242249113 |  | 01/01/2019 |  |
| 32 | Issah Ibrahim | M | Assist. Security Guard | Security | 98478 | J016807160070 |  | 16-Jul-68 |  | 01/08/2000 |  | 024657339 |  | 01/01/2018 |  |
| 33 | Tampori Robert Biisom | M | Chief Headman | Auxiliary | 69684 | H057409270038 |  | 27-Sep-74 |  | 01/11/2000 |  | 0200464523/0246486318 |  | 09/10/2019 |  |
| 34 | Osumani Salifu | M | Chief Headman | Auxiliary | 85018 | J067207010778 |  | 01-Jul-72 |  | 01/05/2001 |  | 246573677 |  | 01/01/2018 |  |
| 35 | Sarpong Georgina | F | Chf Headman | Auxiliary | 733349 | F166905150023 |  | 15-May-69 |  | 15/05/2009 |  | 0546571571 |  | 06/01/2017 |  |
| 36 | Awuah Lydia | F | Chief Headman | Auxiliary | 773230 | F087603050021 |  | 05-Mar-76 |  | 02/08/2010 |  | 0244037455 |  | 01/01/2018 |  |
| 37 | Atondema Akwasi | M | Sanitary Foreman | Auxiliary | 925476 | J047007010955 |  | 01-Jul-70 |  | 01/06/2013 |  | 0246023017 |  | 01/06/2021 |  |
| 38 | Konadu Mavis | F | Sanitary Foreman | Auxiliary | 925480 | F088309010041 |  | 01-Sep-83 |  | 01/06/2013 |  | 244385573 |  | 01/06/2021 |  |
| 39 | Adubea Beatrice | F | Chief Headman | Auxiliary | 6030 | F086807220024 |  | 21-Jul-68 |  | 01/02/1990 |  | 0200829922 |  |  |  |
| 40 | Joyce Amanin | F | Labourer | Auxiliary | 1537128 | F088708310023 |  | 31-Aug-86 |  | 01/06/2022 |  | 545978604 |  |  |  |
| 41 | Mary Darkwah | F | Labourer | Auxiliary | 1544990 | F088405220025 |  | 22-May-86 |  | 01/06/2022 |  | 540572431 |  |  |  |
| 42 | Alidu Abubakari | M | Assist.Security Guard | Security | 773226 | H016907013532 |  | 13-Jul-69 |  | 02/08/2010 |  | 0275480892 |  | 08/01/2017 |  |
| 43 | Sulemana Issah | M | Watchmen-Day | Security | 712258 | J108007010096 |  | 15-Jun-79 |  | 01/10/2008 |  | 0545960856 |  |  |  |
| 44 | Amadu Musah | M | Asst. Security Guard | Security | 727785 | H047107010438 |  | 03-Mar-67 |  | 03/03/2009 |  | 0542167325 |  | 01/05/2021 |  |
| 45 | Tanimu Mohammed | M | Asst. Security Officer | Security | 1541666 | H068007010176 |  | 01-Jul-80 |  | 01/06/2022 |  | 594370972 |  |  |  |
| 46 | Emmanuel Boadi | M | Asst. Security Officer | Security |  | F379007010012 |  | 01-Jul-90 |  | 01/06/2022 |  | 241680782 |  |  |  |
| TRANSPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 47 | Owusu Victor | M | Prin. Transport/Road Off | Drivers | 882118 | G257207010013 |  | 06-Jun-72 |  | 02/01/2011 |  | 0246251785 |  | 02/01/2015 |  |
| 48 | Yaw Dormaa | M | Snr.Transport Officer | Drivers | 602208 | F087906120015 |  | 12-Jun-79 |  | 01/09/2006 |  |  |  | 09/01/2017 |  |
| 49 | Baa Kwasi | M | Snr.Transport/Road Officer | Drivers | 21728 | F077303260017 |  | 26-Aug-65 |  | 04/09/1989 |  | 0200346181/0243428588 |  | 09/01/2017 |  |
| 50 | Arthur Peters | M | Transport/Road Officer | Drivers | 602195 | F087307010135 |  | 06-Aug-73 |  | 01/03/2006 |  | 0543533085 |  | 09/01/2017 |  |
| 51 | Abdul Bashiru | M | Heavy Duty Driver | Drivers | 727779 | F087604070016 |  | 07-Apr-76 |  | 05/05/2009 |  | 0243670333 |  | 15/05/2016 |  |
| 52 | Salifu Osmanu | M | Senior Transport Officer | Drivers | 71762 | F017208280071 |  | 01-Aug-72 |  | 01/06/2000 |  | 244167228 |  | 03/01/2018 |  |
| 53 | Albert Owusu Ansah | M | Driver Grade III | Drivers | 1265159 | F017408080211 |  | 08-Aug-74 |  | 01/03/2018 |  | 0243745004/0204805910 |  |  |  |
| 54 | Adjei Samuel | M | Driver Grade III | Drivers | 1537469 | F089212070356 |  | 07-Dec-92 |  | 01/06/2022 |  | 542698257 |  |  |  |
| 55 | Sosu Nicholas | M | Driver Grade III | Drivers | 1546514 | F089312060016 |  | 06-Dec-93 |  | 01/06/2022 |  | 555804090 |  |  |  |
| 56 | Akuoku Prince | M | Driver Grade III | Drivers | 1546494 | F089111010013 |  | 01-Nov-91 |  | 01/06/2022 |  | 543012127 |  |  |  |
| REVENUE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 57 | Robert Gyabaah Kyeremeh | M | Prin. Revenue Supt. | Revenue | 57179 | G057907300019 |  | 30/07/1979 |  | 01/01/2000 |  | 553707325 |  |  |  |
| 58 | Kesewaa Henrrieta | F | Higher Reve. Inspector | Revenue | 925474 | F088611110021 |  | 11-Nov-86 |  | 01/03/2013 |  | 0249546800 |  | 06/01/2016 |  |
| 59 | Acheampong Anthony | M | Revenue Inspector | Revenue | 32175 | F086507010079 |  | 07-Jul-65 |  | 01/07/1981 |  | 0244487182 |  | 01/06/2015 |  |
| 60 | Osei Opoku | M | Revenue Collector | Revenue | 718310 | F087701190015 |  | 19-Jan-77 |  | 01/10/2008 |  | 0541065298 |  |  |  |
| 61 | Isaac Addai | M | Higher Reve. Inspector | Revenue | 882004 | f026703100014 |  | 10-Mar-67 |  | 02/01/2012 |  | 545421362 |  | 01/03/2017 |  |
| 62 | Asomadu Kwame | M | Revenue Collector | Revenue | 913736 | F08800150059 |  | 15-Mar-70 |  | 28/05/2013 |  | 0246404927 |  |  |  |
| 63 | Florence Owusu Ansah | F | Inspector | Revenue | 6049 | FO16205120045 |  | 28-Jul-63 |  | 01/06/1980 |  | 545800910 |  | 09/08/2011 |  |
| MIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 64 | Anthony Assuah Junior | M | Asst. Programmer | Computer/MIS | 1343236 | F018309130176 |  | 13-Sep-83 |  | 15/08/2019 |  | 246401317 |  | - |  |
| PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 65 | Gyamfi Joseph Atta | M | Procure/Supply Off | Procurement/Supply | 1198127 | F018305060212 |  | 06-May-83 |  | 01/11/2015 |  | 0244186179 |  |  |  |
| 66 | Boamah Seth Yeboah | M | Asst. Procure/Supply Off | Procurement/Supply | 1265136 | F018808040513 |  | 04-Aug-88 |  | 24/04/2018 |  | 0243006068 |  | - |  |
| DEPARTMENT OF URBAN ROADS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 67 | Yanzu Francis Alex | M | Engineer | Engineering | 16544 | F018011230015 |  | 22-Nov-79 |  | 25/06/2003 |  | 244580338 |  |  |  |
| WORKS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 68 | Daniel Yaw Fobi | M | Engineer | Engineering | 512143 | A057404150039 |  | 15-Apr-74 |  | 11/01/2005 |  | 242113683 |  | 01/01/2019 |  |
| 69 | Darkwa Kwame | M | Engineer | Engineering | 59561 | F127612110013 |  | 11-Dec-76 |  | 20/05/2002 |  | 0244614490 |  | 09/07/2016 |  |
| 70 | Farouk Armah | M | Asst. Engr | Engineering | 1506479 | B049006280016 |  | 28-Jun-90 |  | 27/10/2021 |  | 558336692 |  |  |  |
| SOCIAL WELFARE /COMMUNITY DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 71 | Jerry Kofi Hagan | M | Snr. Social Dev. Officer | Social Development | 915311 | F017909070130 |  | 07-Sep-79 |  | 26/10/2012 |  | 547954195 |  |  |  |
| 72 | Frimpong Isaac | M | Social Dev. Officer | Social Development | 929073 | H098308100011 |  | 10-Aug-83 |  | 01/07/2013 |  | 0246943363 |  | 07/01/2018 |  |
| 73 | Aisha Agyeiwaa Abdallah | F | Asst. Social Devt Ofiicer | Community Development | 1536131 | F168606010025 |  | 01-Jun-87 |  | 19/11/2021 |  | 246299371 |  |  |  |
| 74 | Baafi Emmanuel Amaning | M | Asst. Community Dev. Asst. | Community Development | 927244 | F018407300136 |  | 30-Jul-84 |  | 07/07/2013 |  | 0541483070 |  |  |  |
| 75 | Akurugu Eunice | F | Snr. Social Dev. Assistant | Community Development | 1347447 | F039511150060 |  | 15-Nov-95 |  | 13/08/2019 |  | 540711404 |  |  |  |
| 76 | Osei Samuel Boateng | M | Principal Mass Education Officer | Community Development | 928374 | F098512080016 |  | 08-Dec-85 |  | 01/12/2012 |  | 0248904623 / 0503107311 |  | 02/01/1900 |  |
| AGRICULTURAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 77 | Daniel Kofi Agyare | M | Prin. Agric Officer | Agricultural | 127637 | D047906220018 |  | 22/06/1979 |  | 01/11/2004 |  | 208537498 |  |  |  |
| 78 | Ocloo Raymond Quarshie | M | Prin. Agric Officer | Agricultural | 79634 | H016708310017 |  | 31-Aug-67 |  | 14/11/1994 |  | 0208062085 |  | 01/03/2021 |  |
| 79 | Gamah Isaac | M | Asst. Chief Technical Officer | Technical | 599633 | F087602020011 |  | 02-Feb-75 |  | 08/02/2006 |  | 0205294983 |  | 01/10/2021 |  |
| 80 | Apraku Richmond | M | Asst. Chief Technical Officer | Technical | 124760 | G067905060011 |  | 06-May-79 |  | 25/11/2008 |  | 0243375217/ 0209338686 |  | 01/10/2021 |  |
| 81 | Abu Isaac | M | Production Officer | Agricultural | 922011 | F089203160052 |  | 16/03/1992 |  | 25/03/2019 |  | 543212369 |  | - |  |
| 82 | Apandago Frederick Anaaba | M | Production Officer | Agricultural | 1126781 | J119204180018 |  | 18/04/1992 |  | 04/02/2019 |  | 247004058 |  | - |  |
| 83 | Oduro Joseph | M | Production Officer | Agricultural | 1184261 | F069009220019 |  | 22/09/1990 |  | 04/02/2019 |  | 541377367 |  | - |  |
| 84 | Manu Godson | M | Snr.Technical Officer | Technical | 195480 | F376310290014 |  | 01-Jul-71 |  | 01/02/1985 |  | 0548357808/0207294849 |  | 01-14-18 |  |
| 85 | Botuo Nkansah | M | Chf Technical Officer | Technical | 58855 | E126809260016 |  | 26-Sep-68 |  | 03/03/2002 |  | 0246698298 |  | 03/03/2018 |  |
| 86 | Akogo Victor Kafui | M | Agric Officer | Agricultural | 518349 | C058107080010 |  | 08-Jul-80 |  | 01/11/2004 |  | 0260876146 |  | 06/01/2018 |  |
| 87 | Stephen Ayeh | M | Prin. Technical Asst. | Technical | 850338 | E016905050037 |  | 05-May-69 |  | 01/03/2003 |  | 545572864 |  | 20/06/2021 |  |
| 88 | Yaw Kedja | M | Technical Officer Gd I | Technical | 719226 | F0185052560618 |  | 25-May-85 |  | 24/09/2014 |  | 542469938 |  | 23/10/2016 |  |
| 89 | Duodu Faustina | F | Snr Technical Officer | Technical | 718672 | F01871101006 |  | 01-Nov-87 |  | 01/09/2012 |  | 0246087353 |  | 09/01/2016 |  |
| ENVIRONMENTAL UNIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 90 | Jacob A. Owusu | M | Asst.Chief Environ. health offi. | Environmental | 600898 | F177610110016 |  | 11/10/1976 |  | 09/10/2006 |  | 242981932 |  | 01/02/2020 |  |
| 91 | Ronald Bonsu Opoku | M | Asst. Env.Health Analyst | Environmental Health | 1534370 | F249007020018 |  | 02-Jul-90 |  | 27/10/2021 |  | 241282806 |  |  |  |
| 92 | Acheampong Frederick | M | Principal Environ Health Asst | Env. Health and Sanitation | 718924 | E178611160032 |  | 06-Nov-83 |  | 01/11/2012 |  | 0240691479 |  | 20/03/1900 |  |
| 93 | Duah Comfort Sarpong | F | Environ Health Officer Gd1 | Environmental Health | 843265 | F138912290025 |  | 29-Dec-89 |  | 02/09/2016 |  | 0247658406//0542511756 |  | 09/01/2018 |  |
| 94 | Belabe Elizabeth | F | Snr Envn. Health Asst | Environmental Health | 903140 | H088503010045 |  | 01-Mar-85 |  | 02/09/2016 |  | 0247942406 |  |  |  |
| 95 | Danso Marfo Priscilla | F | Environ. Health Asst. | Environ. Health | 1394251 | F249310110026 |  | 11-Oct-93 |  | 21/09/2020 |  | 547207715 |  | - |  |
| 96 | Irene Baidoo | F | Environ Health Off Gd II | Environmental Health | 1353348 | C019810270240 |  | 27-Oct-98 |  | 24/07/2020 |  | 547726682 |  | - |  |
| 97 | Nankaat Emmanuel Baturin | M | Environmental Health Asst | Env. Health and Sanitation | 1405539 | H149003210014 |  | 21-Mar-90 |  | 24/07/2020 |  | 240321764 |  |  |  |
| 98 | Charles Akparibo | M | Environmental Health Asst | Env. Health and Sanitation | 1506369 | J109106060012 |  | 06-Jun-91 |  | 27/10/2021 |  | 247983726 |  |  |  |
| PHYSICAL PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 99 | Adikah Richard | M | Asst. Physical planner | Physical Planning | 1334434 | D118406010035 |  | 01-Jan-84 |  | 22/09/2020 |  | 249452519 |  | - |  |
| 100 | Justice Frimpong | M | Tech.Officer Gd I | Physical Planning | 883229 | F258203240015 |  | 24-Mar-82 |  | 05/03/2012 |  | 244575653 |  | 08/01/2018 |  |
| 101 | Awuah Dormah D. Daniel | M | Tech. Assistant | Physical Planning | 1541657 | B089108230012 |  | 23-Aug-91 |  | 01/06/2022 |  | 547080454 |  |  |  |
| 102 | Azumah Charles | M | Snr. Gardener | Physical Planning |  | F087708220014 |  | 22-Aug-77 |  | 01/06/2022 |  | 247903578 |  |  |  |
| 103 | Osei Kwadwo | M | Tech. Assistant | Physical Planning | 1545012 | F088206150012 |  | 15-Jun-82 |  | 01/06/2022 |  | 249538234 |  |  |  |
| STATISTICS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 104 | Siddique Enusah Abubakar | M | Asst. Stastistician | Stastistics | 1466336 | C018410040677 |  | 04/10/1984 |  | 15/07/2021 |  | 277067720 |  | - |  |

## 3.6 Composite Budget Issues

Summary of 2022 MMDA Budget and Funding Sources - Table 7

| ITEM | ASSEMBLY’S IGF | GOG | DACF | DDF | OTHERS (CIDA&GPSNP) |
| --- | --- | --- | --- | --- | --- |
| TOTALS | 848,000.00 | 2,201,049.84 | 5,057,609.94 | 1,291,250.20 | 569,014.87 |
| GRAND TOTAL | 9,966,924.85 |  |  |  |  |

The Assembly’s projected expenditure for the year 2022 were as follows; GHc 3,363,987.78 for Central Administration, GHc 3,167,573.07 for Works Department, GHc 1,195,599.22 for Department of Agriculture, GHc 321,547.33 for Social Welfare and Community Development, GHc 107,012.02 for Physical Planning, GHc 831,555.53 for Education, Youth and Sports, GHc 55,000.00 for Disaster Prevention and Management, GHc869.653.86 for Health and GHC 55,000.00 for Finance.

## 3.7 Security Issues in the Municipality

The Municipality was relatively calm and peaceful during the period under review except for few infractions which occurred at the Community Mining Site. The Municipal Security Council held periodic meetings to review security situations and also took pre-emptive measures to combat crime and as a result, crime wave and motor accidents have decline considerably.

## 3.9 38 th National Farmers Day Celebration.

The Municipal version of the 38th National Farmers Day was held on Friday, 2nd December 2022 at Asuhyiae under the theme “Accelerating agricultural productivity through value addition.  Below are the details of areas of farming as the overall Municipal Best Farmer.

Details of Municipal Best Farmer-Table 9

| HON. EMMANUEL ADJEI DARKO AGE: 42 |  | AWARDS |
| --- | --- | --- |
| LOCATION: KENIAGO ENTERPRISES |  |  |
| COCOA | 150 ACRES | 1 MOTORCYCLE |
| CABBAGE | 2 ACRES | 10 CUTLASSES |
| PLANTAIN | 10 ACRES | I KNAPSACK SPRAYER |
| RICE | 3 ACRES | 1 RADIO SET |
| OIL PALM | 15 ACRES | 1 FULL PIECE OF CLOTH |
| LIVESTOCK |  | 1 PAIR OF WELLINGTON BOOT |
| LOCAL BIRDS | 100 | ASSORTED AGROCHEMICALS |
| SHEEP | 39 |  |
| GOAT | 60 |  |
| DUCKS |  |  |
| FARMING EXPERIENCE | 22 YEARS |  |

Social Responsibility: helped in Construction of Pipe in the Community

# 4.0 REPORTS FROM THE DEPARTMENTS OF THE ASSEMBLY

## 4.1 DEPARTMENT OF SOCIAL WELFARE AND COMMUNITY DEVELOPMENT

### 4.1.1 Justice Administration:

a) Court Cases: The Family and Juvenile Court continues to administer justice within the municipality. A total number of twenty-four (24) cases were handled by the court. There were nineteen (19) family tribunal cases and five (5) juvenile cases.

All the Juveniles were convicted of three counts: Causing unlawful damage contrary to section 172(b) of the Criminal Offences Act 29(1960), Unlawful Entry: contrary to section 152 of the Criminal Offences Act 29(1960) and Stealing: contrary to section 124 (I) of the Criminal Offences Act 29(1960).

The juveniles were committed to the Maamobi Correctional Centre for a period of 36 months each.

### 4.1.2 Child Right Promotion and Protection:

a) Day Care Centres:

Day Care visitation is part of Child Rights and Protection Program and is to ensure every child of school going age has the right to basic education and early childhood education with a serene environment to promote learning.  The number of registered Day Care Centres with the Department within the Ahafo Ano North Municipal are sixteen (16) with three (3) centres yet to be registered.

I. Number of visits to day care centers during the year under review were ten (10).

II. Three meetings were held with proprietors to discuss issues affecting school management.

b) Case Work:  Number of cases reported was 49 during the year 2022.

Table 1 below shows details of the performances

| ACTVITIES | PERFORMANCES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BF |  | NEW |  | AGES |  |  | RESOLVED |  |  | PENDING |  |  | REFERRED TO FT |  | TOTAL |  |
|  | M | F | M | F | 0-5 | 6-11 | 12-17 | M | F | M |  | F | M |  | F | M | F |
| CHILD MAINTENANCE |  |  |  | 28 | 14 | 5 | 1 |  | 20 |  |  | 6 |  |  | 2 |  | 28 |
| CHILD CUSTODY |  |  | 4 |  | 3 | 1 | 3 | 3 |  |  |  |  |  |  | 1 |  | 4 |
| FAMILY RECON |  |  | 4 | 10 | 4 | 1 |  |  | 10 | 2 |  | 1 | 1 |  |  | 4 | 10 |
| PATERNITY |  |  |  | 2 | 1 |  |  |  | 1 |  |  |  |  |  |  |  | 2 |
| INTERSTATE |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |
| ACCESS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GENERAL ADVICE/WELFARE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTALS |  |  | 9 | 40 | 22 | 7 | 4 | 3 | 31 |  |  | 7 |  |  | 3 | 5 | 44 |

From the table above, out of the total 49 reported cases;

* 36 were resolved which represents 73.4% of the total cases arbitrated during the period under review.

* 2 cases were referred to the court which represents 0.1%

* Thirteen (13) cases which represent (26.5%) are still pending, that is, both the complainants and the respondent did not even report to the office.

c) Rent Dispute Cases:

Seven (7) rent disputed cases were reported and four of the cases were settled amicably. Three are still pending.

### 4.1.3 Community Care:

a) Hospital Welfare:

There were two (2) referral cases who were abandoned by their family members during the year under review.

| No. of Abandoned cases | M | F |
| --- | --- | --- |
| 2 | 1 | 1 |

b) Persons with Disability:

Number of persons (PWD’s) registered =514, 236 Ms and 278 Fs

Blind is =121, Deaf and Dumb=136, Physically Challenged 257

Number of disability fund disbursements done in 2022 is = 1

Number of PWD’s who have benefited from the fund in 2022 = 31

Ms = 18 and Fs = 13.

Blind = 5, Deaf and dumb 7, physically challenged = 21

c) Leap Activities:

During the year under review, there were six (6) grants paid to beneficiary households under the Livelihood Empowerment Against Poverty (LEAP) that is, from 75th to 80th payments cycles were made from 14th to 18th June, 2022. Total amount allocated to the Municipal was GHC531,588.00 Out of the total amount, GHC531,58.00 was credited.

A total of 1,212 households benefited from the programme with a cash out of GHC519,428.00 remaining GHC12,160.00

NHIS- Biometric Registration

There were seventy (70) LEAP beneficiaries whose NHIS biometric registration expired and were recommended for renewal.

| No. of renewal | M | F | TOTAL |
| --- | --- | --- | --- |
| 70 | 22 | 48 | 70 |

### 4.1.4. Mass Education

Mass Education on the following programmes were organized within the year under review:

- Effects of teenage Pregnancy

- Violence against women and children

- Dangers and effects of Child Labour

4.1.4.1. Teenage Pregnancy

Teenage pregnancy is one of the social problems that affects the youth in the municipality. Among the cases recorded at the agency, it was observed that four (4) out of every fifteen (15) cases were teenage pregnancy and more so, neglected by the men who were responsible.  In view of this, sensitization on teenage pregnancy were held across the communities in the municipality. The sensitization highlighted the negative effects of teenage pregnancy such as low birth weight, complications of mother’s pregnancy and delivery, health problems associated with poor perinatal outcomes, greater risk of perinatal death, low IQ and low academic achievement.

4.1.4.2. Violence against Women and Children

Sensitization on violence against women was carried out within some communities in the Municipality.  Education on aggressive behavior typically involving violence abuse of a spouse or a partner with specifically reference to domestic violence Act 2007 (Act 732) was trumpeted. Issues such as forced and early marriages, sexual violence including conflict-related sexual

Violence, emotional abuse, trafficking and Female genital mutilation abuse were also projected.

4.1.4.3 Child Labour Activities:

Community sensitization on child labour was carried out during the year under review. It was emphasized that children who work as labourers by carrying heavy loads, working with dangerous blades or tools, expose to toxic pesticides or fertilizers risk the possibility of ending up in a cycle of poverty.  Communities with child protection committees were advised to do their work diligently to protect the rights of the children in their catchment area. Parents were cautioned to be mindful of the workload that may have adverse impact on their children physical development.

Similarly, under the cocoa life project, NGOs sponsored by Mondelez International championed child labour activities and this resulted in the formation of Child Protection Committees in many of the Area Councils including the formation of the Municipal Child Panel Committee.

4.1.4.4 Collaboration with Voluntary Organizations:

The Office continues to collaborate with NGOs such as Mondelez International, Care International, Child Right International, Right to Play, Voluntary Services Overseas and World Vision Ghana in the municipal.

For instance, World Vision in collaboration with the Municipal Assembly donated bicycles to pupils who walked long distances to school in 25 different communities. Secondly, the department in partnership with Right to Play (NGO) sensitize school children, teachers and parents on child right issues.

  - GHANA EDUCATION SERVICE

    - Key Activities Identified For Performance

4.2.1.1. Monitoring and Supervision

4.2.1.2. Teaching and Learning Resources

4.2.1.3. BECE 2022

4.2.1.4. Teacher Professional Development

      - Reconstitution of Municipal Education Oversight Committee

4.2.1.6. Teachers Industrial Strike Action

4.2.1.7. National Standardized Test for B2 and B4

### 4.2.2. Basic Education:

No. of KG Schools              	: 		77

No. of Primary Schools      	:     		76

No. of JHS                             	:		65

No. of SHS                             :		2

No. of drop out, Basic   School:		23

4.2.2.1. Pupils Enrolment Status

KG                       				4,783

PRIMARY            				12,260

JHS                          				5,282

TOTAL              				22,325

4.2.2.2. Staff Establishment

KG                                            		250

PRIMARY                               		496

JHS                                           		425

TOTAL NO. OF TEACHERS.            	1,171

TEACHER- PUPIL RATIO  			1: 23

BECE PASS RATE             			98.5%

NO. SCHOOLS UNDER SCHOOL FEEDING      : 47

NO. OF PUPILS ENJOYING SCHOOL FEEDING: 12,799

4.2.1.1 Monitoring and Supervision

The Municipal Director, the Head of Inspectorate and Supervision and the Trekking officers monitored all the KG/ Primary, Junior High Schools and SHS in the Municipality to check on school environment, school feeding and teaching and learning activities.

4.2.1.2. Teaching and Learning Resource

The Ministry of Education and the Ghana Education Service (GES) in collaboration with the Family Health International 360 (FHI360), USAID: Learning supplied assorted text books to B1, B2 and B3 Pupils to all the 63 GALOP Schools in the Municipality. The Transition to English materials included pupils’ textbooks, read aloud compendium, a set of word card, pupils’ workbooks, Teachers’ Guide.

a) Management Efficiency

The directorate monitored the end of term   one assessments in all Basic Schools in the municipality. School heads were directed to supervise the assessments that were based on Literacy and Numeracy for KG and Lower primary, English and Mathematics for upper primary and the CORE Subjects for JHS.

b) Workshop

The Girl Child Education Unit of the directorate organized a one-day sensitization seminar for all school-based facilitators in the municipality. This capacity training programme was scheduled on two cohorts on 31st March and 1st April, 2022 respectively.

After the address by the municipal director of education, participants were taken through among others such as the history, mission and vision of Girl Child Education Unit, contemporary issues and leadership challenges in the GCU, enrolment and retention of the girl child etc. Ninety-two participants attended the workshop, seven Ms and eighty-five Fs.

c) Stakeholders Engagement

Ahafo Ano North Municipality has three paramountcy thus Tepa, Manfo and Mabang traditional areas. The newly assigned municipal director of education paid a courtesy call on the Omanhene of Tepa and Manfo Traditional Areas. The chiefs were happy to receive the municipal director, GES. They all pledged their support to rally behind her to succeed in her tenure of office.

d) Computerized School Selection and Placement System (CSSPS)

Upon the receipt of a long list of names of 2022 BECE candidates who were placed in various SHS/SHTS, it was reported that those found on the list had not been enrolled as of the time of publication. About

Five hundred and sixty out of the list were candidates from the municipality.

One hundred and seventy of the contacts have been made so far. Most candidates were found to have been enrolled after the Easter holidays. About seven of those we have contacted so far stated categorically that they were not interested in further education and that, they were preparing to enter into apprenticeship. Some of them also complained about the tall list of prospectus and the associated cost of the items. Lack of funds kept them out of school.  We have not been able to establish contact with some of the parents due to poor or no network in some communities.

4.2.1.3. 2022 Basic Education Certificate Examinations

The 2022 BECE started on Monday, 17th October, 2022 to Friday, 21st October 2022. The examinations were conducted in 8 centers in the Municipality. The Municipal Director of Education, the Municipal Chief Executive, and the Director General of NADMO all visited the various exams centers to encourage the candidates and ensure the smooth conduct of the examinations. A total of 1867 candidates sat for the examination with 20 absentee candidates. Six Females were heavily pregnant. There were three nursing mothers.

4.2.2.3. Teacher Professional Development

The Ministry of Education and the Ghana Education Service (GES) in collaboration with the Family Health International 360 (FHI360), USAID: Learning supplied assorted text books to B1, B2 and B3 Pupils in the GALOP Schools. The Transition to English materials included pupils’ textbooks, read aloud compendium, a set of word card, pupils’ workbooks, Teachers’ Guide.

A two-day training schedule was designed for a workshop for B1, B2 and B3 teachers and Head teacher in three cohorts dated from 5th to 12th December, 2022. A total of 236 teachers, 141 Ms and 97 Fs participated in all the three centers from the 63 GALOP Schools in the Municipality.

The topics treated among others included: Rationale for Transition to English (T2E), Differences between L2 and L1. Instructional Routines and how to use them, Overview and Key Features of the B1, B2 and B3 Materials, Learning Language through Rhyme, song and chant, Teaching Vocabulary and Comprehension, In-School Support: PLC and Coaching, Identifying and supporting struggling Readers, Conducting and Recording Annual School Educational Status (ASER) and Remediation.

4.2.2.7. School Sanitation Solutions Challenge

The World Vision International, received entries of about 800 hand-written essays on plans to end Open Defecation. Three girls from Tepa SDA JHS submitted their entries. Two out of the three were short-listed for Master Champions in Accra. Miss Maria Abubakari Wuntarli of Tepa SDA JHS 2 qualified for the Grand Final in Accra on August 21, 2022. She was the 1st Runner-up. She was gifted with a school bag, a diary and a Samsung galaxy tablet. The school was presented with 10 dustbins, rakes and shovels. The trip of the grand final was sponsored by Ahafo Ano North Municipal Assembly.

4.2.2.8. USAID Learning Support

The USAID: Learning in collaboration with the Ministry of Education (MoE) and the Ghana Education service (GES) have started the implementation of the T2E Programme in all the USAID Support schools. Thirteen of the primary schools in the Municipality are under the programme. The implementation of the T2E Programme in the classrooms by teachers are specially reinforced by language experts through Ghana Radio Lessons. The Lessons are targeted at B1, B2 and B3 Learners only.

Seven (7) officers and facilitators who have received training on T2E Material Implementation were selected to moderate the programme on MPUNTUO FM 93.4 MHZ, Tepa. The team is led by a Supervisor, a Coordinator and a DTST.

The team visit the Radio station on Mondays, Wednesdays and Fridays to moderate the 1hour live lessons. The lesson began each day at 10:30am to 11:30am. The monitoring team headed by the Municipal Director of Education visited the schools to ensure compliance and adherence to the programme guidelines. A software on ODK has been developed for periodic assessment and teacher support activities. .

4.2.2.9. WASSCE and BECE 2022 Report

1. The West African Examinations Council, WAEC conducted the 2022 written WASSCE Papers in August through to September, 2022 throughout the country.

2. Mabang SHTS registered 331 candidates, 230   Ms and 151 Fs. There were no pregnancy cases but 1 nursing-mothers. The total number of absentees were 5

3. Tepa SHS registered 919 candidates, 487 Ms and 432 Fs. There were 2 absentees. There were two pregnant cases recorded at Tepa SHS

4. The 2022 WASSCE was generally peaceful. However, some students were caught with foreign materials at both centers and were asked by the external supervisor to write reports.

5. The BECE 2022 was conducted from 17th to 21st October, 2022 in 8 centers in the Municipality.

6. There were 1,867 Candidates who sat for the examinations, 1060 Ms and 807 Fs. 6 pregnant girls, 3 nursing mothers and a total of 10 absentees.

7. Out of the 8 centers, 2 recorded a form of exams malpractice.

8. At examination Centre Number 50902 and Centre Name: Manfo R/C Primary, two students were caught with foreign materials and were made to complete Irregularity Form during the ICT paper.

9. At examination Centre Number 50901 and Centre Name: Tepa SHS A, on 20th October, 2022, during the period of the Integrated Science Paper for the morning session, a strange person who was later identified as a staff of WAEC from Sunyani , entered the exams Centre without any official  introduction. He was confronted by the Supervisor of the center as the supervisor took him for one of the Basic School teachers who was trying to find himself into one of the examination rooms.

10. After some short verbal exchanges by the supervisor with the said official, the supervisor received a call from Controller, Kumasi-Ashanti, that the gentleman in question was a staff member of WAEC and should be allowed to work.

11. The supervisor and the invigilator who were involved in that incident were asked to report to the Controller in Kumasi after the examinations. The two have since submitted their written reports awaiting a determination by the Council. Some few other students were also made to fill out irregularity forms when they were found with foreign materials.

## 4.3 NATIONAL HEALTH INSURANCE SCHEME (NHIS)

### 4.3.1 Registration

In 2022 the Municipal Office of NHIS registered a total number of 45,646 clients. Out of the total registrants, 7,328 were new members and 34,741 were renewals of cards.

4.3.2 Registration of the Poor

The Municipal Office continues to register the poor and vulnerable to enjoy benefits accruing to members on the scheme. As at the end of the year 2022, the Municipal Office registered the following categories of the poor.

Pregnant Women                		 1,859

Indigent                               		 1,718

### 4.3.3 Innovative Programme

The Scheme in the course of operations introduced some innovative programs to boost the membership drive and improved the operational efficiency.

Mobile renewal was introduced to help members to renew their cards at their own convenience via the short code *929# and equally link their NHIS Cards to Ghana Cards to enable members attend hospital with their Ghana Cards.

Childhood cancer was also included in the benefits package of the National Health Insurance Scheme.

## 4.4. GHANA NATIONAL FIRE SERVICE

### 4.4.1. Activities Carried Out During the Year

4.4.1.1. Fire Safety Education and Audit

The Tepa Fire Station Command undertook safety education and safety audit at the Tepa market, shops/stores, educational institutions, hospitals, financial institutions, public institutions, public and private residences, hotels and guesthouses, cocoa depots, churches, warehouses, mechanic/fitting shops, training centers, and fuel/LPG filling stations to ascertain the adequacy of fire safety measures put in place by management of establishments for life and property property protection on the premises.

4.4.1.2. Rural Fire Programme

The command undertook anti-bush fire campaign in some selected communities within municipality. The command during the campaign train fire volunteer squads to help educate the residents of the communities about the dangers and prevention of both domestic and bush fires.

The command successful trained thirty-four (34) fire volunteers at Suponsu, Asukese, Adadekrom and Akwasiase.

4.4.1.3. Incidents

The Fire Station responded to a total of forty-six (46) incidents within the municipality in the year under review.

| INCIDENTS |  | NUMBER |
| --- | --- | --- |
| FIRES | Domestic | 8 |
|  | Bush | 10 |
|  | Vehicular | 8 |
|  | Commercial | 4 |
|  | Institutional | 0 |
|  | Industrial | 0 |
|  | Electrical Installation | 2 |
| ROAD TRAFFIC COLLISIONS (ACCIDENTS) |  | 4 |
| FLOOD |  | 1 |
| FALSE CALLS |  | 9 |
| TOTAL |  | 46 |

## 4.5 PHYSICAL PLANNING DEPARTMENT (PPD)

### 4.5.1 Development Control Measures

This session outline the various development control activities carried out under the period reviewed. This included Technical Subcommittee meetings (TSC), Spatial Planning committee meetings, Joint Site inspections organised by Technical subcommittee in collaboration with Physical Planning department and Works Department. Finally, development application received and processed.

4.5.1.1 Technical Subcommittee Meetings Held

As required by the Land Use and Spatial Planning ACT, 2016 (ACT 925) Section 39 subsection 8 of Act 925, the Technical Sub-Committee (TSC) shall organised meetings and report all recommendations or decisions concluded at their meetings on all development applications vetted and other development control activities to the Spatial Planning Committee for final decisions and considerations. In view of that, monthly meetings were held.

4.5.1.2 Meeting date for Technical Subcommittee in 2022

The Technical Sub-committee held its first meeting on 18th January, 2022 and last meeting on Thursday 15th December, 2022

Table 3.1 shows the date of TSC meetings held

Table 4.5.1 Summary of TSC monthly meetings

| MONTHLY TECHNICAL SUBCOMMITTEE (TSC) MEETING DATES FOR 2022 |  |  |  |  |
| --- | --- | --- | --- | --- |
| NO. | ITEM | MEETING DATE | VENUE | REMARKS |
| 1. | January, 2022 (TSC) Meeting | Tuesday 18th January,2022 | Assembly Conference Hall | Two (2) development applications vetted and recommendation made to SPC |
| 2. | February, 2022 TSC Meeting | Wednesday 16th Feb.2022 | Assembly Conference Hall | Three (3) applications recommended to SPC for consideration and approval |
| 3. | March, 2022 TSC Meeting | Thursday 17th March,2022 | Assembly Conference Hall | Two (2) applications recommended to SPC for consideration and approval |
| 4. | April, 2022 TSC Meeting | Thursday 21st April,2022 | Assembly Conference Hall | Two (2) applications recommended to SPC for consideration and approval |
| 5. | May, 2022 TSC Meeting | Wednesday 18th May,2022 | Assembly Conference Hall | One (1) commercial development application recommended to SPC for consideration and approval |
| 6. | June, 2022 TSC Meeting | Tuesday, 21st June, 2022 | Assembly Conference Hall | Two (2) applications recommended to SPC for consideration and approval |
| 7. | July, 2022 TSC Meeting | Wednesday 20th July 2022 | Assembly Conference Hall | One (1) application recommended to SPC for consideration and approval |
| 8. | August,2022 TSC Meeting | Tuesday 23rd August 2022 | Assembly Conference Hall | Twenty five (25) applications recommended to SPC for final decision |
| 9. | September,2022 TSC Meeting | Wednesday 21st Sept., 2022 | Assembly Conference Hall | Two (2) applications recommended to SPC for final decision. |
| 10. | October 2022 TSC Meeting | Thursday 20th October,2022 | Assembly Conference Hall | Three (3) applications recommended to SPC for final decision. |
| 11. | November,2022 TSC Meeting | Wednesday 23rd November,2022 | Assembly Conference Hall | Six (6) applications recommended to SPC for final decision |
| 12. | December,2022 TSC Meeting | Thursday 15th December,2022 | Assembly Conference Hall | Ten (10) applications recommended to SPC for final decision |

Source: TSC Minutes, PPD, 2022

4.5.1.3 Summary of Matters Discussed at TSC Meetings

Reference to the Minutes of the Technical Subcommittee meetings held, the following are some of the summary recommendations made to Spatial Committee Meeting.

- TSC recommended the demolishing of building built on access road to Beposo (the committee suggested the demolishing is subject to court warrant before any action be taken on the building)

- TSC concluded that compulsory acquisition of EPA and Fire permits of all commercial and Industrial buildings before permits are issued

- Control haphazard development by strictly adhence to implementation of local Plans for permit acquisitions

- Revision of the following local plans which are over ten years of existence: Beposo, Kwame Awuah, Mabang, East Nsuase, West Nsuase, Odumase, Akwasiase and Daafour.

4.5.1.4. Spatial Planning Committee Meetings (SPC)

The Spatial Planning Committee of the all MMDAs shall ensure that physical developments are carried out in their districts in accordance with the Land Use and Spatial Planning Act,2016 (Act925). The SPC as per it function shall ensure that spatial plans are prepared. The SPC is responsible for the preparation of district spatial development framework, preparation of structure plan, deliberate on and approve the recommendation of the Technical Sub-committee, consider and approve applications for permit.

In light of that the Ahafo-Ano North Municipal Spatial Planning committee organised its meetings in accordance of the Land Use and Spatial Planning Act 2016 (ACT925) in spite of inadequate provision of resources. The table 3.2 indicated the SPC meeting dates.

Table 4.5.2 SPC Meetings

| MONTHLY SPATIAL PLANNING COMMITTEE (SPC) MEETING DATES FOR 2022 |  |  |  |  |
| --- | --- | --- | --- | --- |
| NO. | ITEM | MEETING DATE | VENUE | REMARKS |
| 1. | January 2022 SPC Meeting | Thursday 27th January,2022 | Assembly Conference Hall | Approved two (2) development applications and adopted the recommendation of TSC to revised the following local Plans: Beposo, Kwame Awuah, Mabang, East Nsuase, West Nsuase, Odumase and Akwasiase and Daafour as when resources are made available |
| 2. | February 2022 SPC Meeting | Monday 28th February,2022 | Assembly Conference Hall | Approved the two (2) development applications and deferred one |
| 3. | March 2022 SPC Meeting | Thursday 31st March, 2022 | Assembly Conference Hall | Approved one (1) development and deferred application subject to provision od site plan |
| 4. | April 2022 SPC Meeting | Thursday 28th April, 2022 | Assembly Conference Hall | Approved one (1) development and deferred one application subject to provision of site plan and update on Street naming and property addressing plate installation |
| 5. | May 2022 SPC Meeting | Tuesday 31st May, 2022 | Assembly Conference Hall | Approved the one (1) commercial(fuel service station) development application recommended by TSC |
| 6. | June,2022 SPC Meeting | Thursday 30th June, 2022 | Assembly Conference Hall | Approved the two (2) development recommended by TSC |
| 7. | July 2022 SPC Meeting | Thursday, 28th July, 2022 | Assembly Conference Hall | Approved the one (1) development recommended by TSC and presentation on Akwasiase Street naming database |
| 8. | August,2022 SPC Meeting | Wednesday 31st August,2022 | Assembly Conference Hall | Approved the twenty four (24) development recommended by TSC and deferred one (1) applications subject to drawings not being certified by architect |
| 9. | September 2022 SPC Meeting | Thursday 29th September, 2022 | Assembly Conference Hall | Approved two (2) development application recommended by TSC |
| 10. | October, 2022 SPC Meeting | Thursday 27th October,2022 | Assembly Conference Hall | Approved three (3) development application recommended by TSC |
| 11. | November, 2022 SPC Meeting | Wednesday 30th Nov, 2022 | Assembly Conference Hall | Approved six (6) development application recommended by TSC |
| 12. | December,2022 SPC Meeting | Thursday 22nd December,2022 | Assembly Conference Hall | Approved ten (10) development application recommended by TSC |

Source: SPC Minutes, PPD, 2022

4.5.1.5. Summary of Decisions by SPC

Reference to the recommendations by the Technical Subcommittee, the Spatial Committee considered the following:

- Considered fifty eight (58) development applications and gave the approval for fifty four(54) development applications and deferred four (4) applications subject to provision of land documents

- Commence the use of all legal development application forms captured in the Land Use and Spatial Plan Regulations (LI 2384) in 2023

- Demolish the building built on access road to Beposo ( subject to a court order from Tepa magistrate court to be issued to the defaulter)

- Prepare Spatial Plans (Structure plan and SDF)

- Approved Manfo Local Plan

- Considered the revision of the all local plans that were over 5 years

4.5.1.6. Joint Technical Committee Site Inspection

The Technical Sub-Committee prior to its meeting conducted random site inspections on the development applications received.

Table 4.5.3 Site Visited by TSC

| S/N | PROPOSED DEVELOPMENT | LOCATION | REMARK |
| --- | --- | --- | --- |
| 1. | Construction of Fuel Station | Addai Amankwah | Preliminary site inspection conducted |
| 2. | Construction of Fuel Station | Mabang | Site inspection conducted |
| 3. | Civic &culture- Church and Mission house | Daffour | Preliminary site inspection |
| 4. | 5 bedroom apartment –Residential | Odikro Nkwanta | Preliminary site inspection- No approved local Plan of the area |
| 5. | Two story Building – Residential | Wawase | Preliminary site inspection conducted |

Source: Site Inspection report, PPD, 2022

4.5.1.7. Development Applications Received and Processed

The department received a total number of Fifty Eight (58) development applications during the year. A total number of fifty four (54) development applications were considered and approved by the Spatial Planning Committee. Three of the applications were deferred subject to the provision of land document and the drawing endorsement by licence draughtsman

4.5.1.8 Development Applications Received and Processed

Table 4.5.4 Summary of applications received and processed

| S/N | Zoning Status | Number Received | Proposed Development |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Storey (No. 1 storey Buildings) | Semi-Detached Houses/Building | Detached Buildings |
| 1. | Residential Use | 51 | 4 | 5 | 42 |
| 2. | Commercial Use | 3 | 1 |  | 2 |
| 3. | Mixed Use | 3 | 3 |  |  |
| 4. | Civic & Culture | 1 |  |  |  |
| 5. | Industrial Use | Saw mill factory |  | Temporary structure |  |
| Total |  | 58 | 8 | 5 | 44 |

Source: SPC Minutes December, 2022

4.5.1.9. Number of Applications Deferred

On the above, four (4) applications were deferred. The reason for the deferral were as follows;

- Absence of site plan and allocation paper.

- Drawings not certified by licence draughtsman

- Wrong Coordinates.

### 4.5.2. Street Naming and Property Addressing

Street Addressing System simply involves the naming of all streets and numbering of properties. It entails developing digitized maps and setting up of a District Spatial Database System to be used in the planning and management of urban communities. The Street Addressing System was a presidential directive to all Metropolitan, Municipal and District Assemblies (MMDAs) across the country to implement the project. The project operates under the domain of the Municipal Planning and Coordinating Units (MPCU) and is led by the Physical Planning Department of the Assembly. It is implemented with local resources. The Ahafo- Ano North Municipal Assembly unfortunately happened to not be among the piloted MMDAs supported technically by the German Development Corporation (GIZ).

4.5.2.1. Update on Ground Truthing and Deskwork for 2022 Street Addressing

In the Ahafo- Ano North Precisely Tepa town, parcelling was done using aerial photos and existing local plans, to reflect current ground situation.

- Within the year a total of 105 streets were digitised

- Ninety (90) streets were named

- Seventy  (70) streets have sign post mounted

- A total of 5,316 parcels digitised

- Database for both Temporary Structures and signboard/billboard including street naming and property addressing database with UPNs

- Completion of the Installation of Property addressing plate: A total of 4,461 were received  out which a total of 4,394 was successfully installed

4.5.2.2. Update on Temporary Structure location Map

A data collection was done to map all metal and wooden containers within the Municipal capital. The result from the data collected show that:

- Mental containers:       1,227

- Wooden containers:       205

Total:                              1,432

4.5.2.3 Sign/Billboards

Data collection was carried on sign/billboards within the Tepa Township. From the data collected a total number of One hundred and two (102) signboards or billboard did not have approval from the Spatial Planning Committee before mounting the bill board and this has caused the Assembly to have lost revenue. Figure 2 show in blue symbols the locations of these signboard.

A database was created to help monitor as when any developer intended to mount any of these billboard the department would be contacted.

4.5.2.4. Completion of the Installation of Property Addressing Plate.

- Completion of the Installation of Property addressing plate: A total of 4,461 were received  out which a total of 4,394 was successfully installed

### 4.5.3. Spatial Plans Preparation

The Spatial Plans include the Preparation of Spatial development Framework (SDF), Structure Plan (SP) and Local Plans (LP)

According to the Land Use and Spatial Act 2016, (Act 925) within twelve months of coming into force of a Regional Development Framework, the District Assemblies shall in consultation prepare a District Spatial Development Framework in conformity with the Regional Spatial Development Framework.

In light of that, the Ahafo-Ano North Municipal Assembly engaged in Stakeholders consultation to commence the preparation of the Spatial Plans.

4.5.3.1. Structure Plan and Spatial Development Framework Preparation

The Ahafo-Ano North Municipal is yet to commence the preparation of these spatial plans.

4.5.3.1.1. Action Taken On The Preparation Of SP And SDF

- The Assembly decided to contract a consultant to assist the preparations of the Spatial Development framework and the Structure Plan

- Captured in the Assembly Medium term development plan

4.5.3.2. Reconnaissance Survey

The Land use and Spatial Planning Authority (LUSPA) Accra and the Ashanti LUSPA Regional Director in collaboration with the Environmental Protection Agency (EPA) responsible for the coordination of the Landscape Restoration Option of the On-going Ghana Landscape Restoration and Small-Scale Mining Project (GLRSSMP) on 1st November, 2022 visited the Assembly.  As part of the survey the team interacted with few key members of the Spatial Planning Committee (SPC) specifically the Physical Planning Officer, Development Planning officer, the Municipal Engineer and other relevant staff including the Municipal Coordinating Director. The purpose of this reconnaissance survey in the cocoa landscape is to continue gathering baseline data on physical, culture and socio-economic features and the management structures of the various boards and sub-committee present within these project basins which Ahafo Ano North was part. The team had interaction with the key members of the SPC based on the Questionnaires given.

    - Ghana Secondary City Support Programme (GSCSP)

The Ahafo-Ano North Municipality have been part of the selected MMDAs that are rolled up on the Ghana Secondary City Support Programme. So far the 2020 and 2021 assignments was done. The Department is waiting for the release of funds to carry out the activities stated in the budget.

## 4.6. GHANA POLICE SERVICE

### 4.6.1. Organization and Police Activities:

During the year 2022. The police performed its normal duties such as bank guard, Leap escort, day and night patrols as well as receiving complaints from the public, investigation and prosecution of offenders. The Municipal Commander as part of Police Community relationship engaged in sensitization of public on how to prevent crime, educated them on the rules regarding the purchase of guns, registration and renewals, stealing, narcotics, defilement, abduction etc.

4.6.1.1. Crime Statistics:

Total Number of Cases Reported				         401

Total Number of Cases Refused                   		            0

Total Number of True Cases				         401

Total Number of Cases Closed				           97

Total Number of Cases Sent To Court			            27

Total Number of Cases Convicted 			            18

Total Number of Cases Acquitted and Discharged	              3

Total Number of Cases Awaiting Trial 			              6

Total Number of Cases under Investigation 		           277

Case of Interest							   4

      - Case of Interest:

There were four murder cases in the year under review.  Three out of the four cases are before court.

4.6.1.2. Crime Trend:

Total number of cases recorded during the period under review is 401 as compared to 457 in the year 2021. This shows a decrease of 56 in the crime rate. No Residential and Highway Robbery cases were recorded.

4.6.1.3. Observation

There is a general reduction of crime over the year as compared to the previous year. The general reduction of crime can be attributed to the proactive measures adopted by the Police in combating crime such as intensification of patrols, supervision, and proctiveness and effective intelligence gathering.

  - DEPARTMENT OF AGRICULTURE

### 4.7.1 Districts Activity Implementation Efficiency Ratio

Table 4.6.1 District Activity Implementation Efficiency Ratio

| Unit | Total number of activities planned (1) |  | Total Number of activities implemented and completed (2) |  | Number of activities implemented that are gender sensitive (3) |  | Activity implementation rate (2/1) |  | % of implemented activities that are gender sensitive (3/2) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 |
| Districtsname |  |  |  |  |  |  |  |  |  |  |
| MIS/SRID | 3 | 3 | 2 | 1 | 2 | 1 | 67 | 33 | 67 | 100 |
| CROPS | 0 | 3 | 0 | 1 | 0 | 1 | - | 33 | - | 100 |
| PPRSD | 0 | 1 | 0 | 1 | 0 | 1 | - | 10 | - | 100 |
| WIAD | 0 | 0 | 0 | 0 | 0 |  | - |  | - |  |
| EXT | 0 | 4 | 0 | 2 | 0 | 2 | - | 50 | - | 100 |
| APD | 0 | 0 | 0 | 0 | 0 |  | - |  | - |  |
| ENG | 0 | 0 | 0 | 0 | 0 |  | - |  | - |  |
| VET | 3 | 3 | 3 | 1 | 3 | 1 | 100 | 33 | 100 | 100 |
| Totals | 6 | 14 | 5 | 6 | 5 | 6 | 83 | 42 | 83 | 100 |

Source: DAD, 2022:  Key activities undertaken during the quarter under review included; Field Days, Demonstrations, Market surveys, Veterinary, and National Farmers’ Day celebration etc. Activity implementation efficiency ratio for the period under review stands at 42% compared to the same period the preceding year of 83% recording a decrease of 49.4%. The reduction in approved budget is responsible for the said decline.

      - Institutional Collaboration

MOFA collaborated with the Ghana National Fire Service (GNFS) on bushfire prevention and control and it translated to organisation of fora for farmers in some communities across the municipality.

MOFA also collaborated with Ghana Health Service to educate farmers on HIV/AIDS prevention and control, with the key message as no child should die from HIV AIDS etc.

| Name of Project / Activity | Beneficiaries |  |  |  |  | Achievement (Result from intervention) |
| --- | --- | --- | --- | --- | --- | --- |
|  | M | F | Youth | Aged | PLWD |  |
| Fora on Bush fire prevention and control | 2,048 | 1,470 | 1,899 | 2,578 | 3 | Farmers in two communities decided to form fire volunteer groups by contacting office of the GNFS |
| HIV/AIDS Awareness creation | 245 | 125 | 300 | 65 | 2 | Some few participants have started the advocacy. |
| ## Child labour prevention and Safety protocols on COVID-19 etc. | 112 | 92 | 154 | 44 | 1 | Some farmers ensured strict adherence to the safety protocols |

ANALYSIS: Farmers were educated on the HIV AIDS pandemic its new infection and spread and cautioned on prevention and care. F participation form 88% with remaining 12 % being M. Farmers were also educated on Child labour prevention and Safety protocols on COVID-19 across the municipality.

      - Collaboration with Projects (MoFA)

      - Planting for Food and Jobs (PFJ)

One of the flagship programmes of government Planting for Food and jobs (PFJ) entails field staff technical support to farmers in the adoption of GAP aimed at increasing production. To ensure the success of this programme Fora, education, sensitisation and trainings were conducted for farmers in the utilisation of improved seeds and fertiliser as well as awareness creation on the availability of other vegetables planting materials. Demonstration accompanied by field Days were conducted to teach farmers the methods and results to be obtained from practising some of the technologies so as to eventually adopt them for increased productivity.

The key objective of this programme is to increase productivity of farmers, create jobs reduce youth unemployment as well as produce enough food to feed Ghanaians culminating in food security. The programme cuts cross the Municipality with the various locations as indicated below:

| Name of Project / Activity | Beneficiaries |  |  |  |  | Achievement (Result from intervention) |
| --- | --- | --- | --- | --- | --- | --- |
|  | M | F | Youth | Aged | PLWD |  |
| Use of improved planting material(Maize, Rice, Vegetables) | 4,074 | 2,482 | 6,556 | 1,050 | 3 | Adoption of fertilizer usage, purchase of improved planting material |
| Use of compound fertilizer | 2,871 | 1,040 | 3,911 | 985 | - | Helped to increase yield |
| Use of chemical to control FAW | 184 | 58 | 210 | 15 | - | Decline in destruction by FAW |
| Use of organic fertilizer | 145 | 67 | 212 | 25 | - | Shifting focus of farmers to chemical fertilizer alternative. Improved soil structure |

Source: DAD, 2022

ANALYSIS: Adoption of fertilizer usage, shifting farmers focus on alternative to chemical fertilizer by use of organic fertilizers as well as purchase of improved planting material resulted in increased yield

        - Monitoring and Coordination Reports

A total of 55 monitoring visits were undertaken by MDA/MAOs during the period under review. Activity areas included the following: -

- Fora, education and sensitization on  bushfire prevention and control

- Group meetings, trainings and awareness creation

- Inspection of field of prospective farmers for the National Farmers’ Day Celebration

        - Purpose and Objective Of Monitoring

- To assist in  tracking field activities carried out by AEAs,

- Serves as an evaluation of AEAs activities to ensure quality service delivery to clients.

- To ensure planned activities are duly followed and implemented according to planed programmes and activities outlined.

- It provides opportunities for backstopping sessions and affords management the opportunity to address certain fundamental challenges encountered by field staff and the provision of quick responses to them.

During the period a total of 3,250 farmers comprising 2,550 M and 700 F were present during fora organised on bushfire prevention, group meetings, education, sensitisation, trainings, inspection conducted across the Municipality.

The communities visited included the following: - Twabidi, Achina, Akrofoso, Dwaho, Subriso, Numasua, Asuhyiae, Dompo, Krakosua, Bosikese, Abonsuaso, Anyinasuso, Mabang, Akwasiase.

        - Findings

Main challenges identified by farmers as impediments to their farming activities with its associated implications on productivity are listed below:-

- Dependence on rain fed Agriculture has serious negative impact on yield and productivity

- Farmers also expressed their frustration at poor road networks linking their communities to municipal capital resulting in high post-harvest loss of farm produce

- Use of simple tools in farm operations is drudgery resulting in high operation cost and low productivity

        - Recommendations

- Provision of small irrigation facilities to reduce reliance on rain fed Agriculture

- Rehabilitation of feeder roads for easy access so as to reduce post-harvest losses

- Provision of simple farm implement to farmers at Government subsidize price

4.7.1.4. Crop and Livestock Production

        - Highlights of District Weather Situation

The general weather condition during the period under review was dry with cool nights accompanied by low humidity and high daily temperatures. Majority of crops on the fields suffered from water stress particularly the cereals such as maize, except some rice that were cultivated under bund conditions. Most plants on the field exhibited signs of wilting as rainfall pattern was unfavourable for their growth.

        - Rainfall and its Effect on Agriculture

Rainfall distribution during the period was uneven a condition which affected the growth and development of some cultivated crops particularly Maize and to a lesser extent rice. The first and second month of the quarter (October and November) experienced normal rainfall however, the third (December)  recorded no rainfall at all a situation which in a large extent affected majority of maize that were at tasseling stage and subsequently resulted in the wilting of maize. Rice on the hand experienced mix fortune as those cultivated under bund conditions survived whilst the rest recorded yield loss.

Table 4.6. 2 District Average Rainfall Distribution

| No | District | 2021 |  | 2022 |  | Percentage Change (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Rainfall (mm) | No. of Rain days | Rainfall (mm) | Number of Rain days | Rainfall in (mm) | No. of Rain days |
|  | AANMA |  | 9 |  | 15 |  | 40% |

ANALYSIS: During the period a total of 15 rainy days was recorded compared to the same period the preceding year of 9 showing an increase of 40%. However, the rainfall was unevenly distributed and ended at the month of November with December experiencing no rainfall. Coincidentally that was when majority of Maize tasselled and were cobbing. A condition that   negatively impacted crop yield and production.

The situation impacted negatively on cultivated crops resulting in low yield hence decline in production. An example can cited of maize which was severely affected as majority of the maize field experienced wilting.

        - External factors impacting on agriculture production

            - Flooding

            - Illegal Mining (sand &gold)

            - Bush Fire

            - Alien Herdsmen Activities

            - Poor Road network

            - Price variation of inputs

            - Pest & diseases

            - Others

      - Flooding

Being one of the natural disaster associated with farming, flooding may have very negative impact on Agriculture production. It may inundate several hectares of land and could wipe out several crop produce either harvested or not and the end result will be economic loss and food security threat to the nation. In the municipality some few communities such as Odikronkwanta, King Jesus, Bodesua experienced floods that affected some cultivated rice which resulted in some haven been carried away leading to economic loss to affected farmer

      - Fall Army Worm

The extent of damage posed by these pest recorded dramatic decline in the Municipality during this time of the years under review. The proactive extensive fora and sensitization conducted by DADU staff in all operational areas across the Municipality on the menace posed by the FAW, the adoption of   preventive and control measures helped to combact their spread.

      - Illegal Mining (sand &gold)

This activity is the most devastating form of land degradation and poses the greatest threat to Agriculture production with the propensity to cause food insecurity leading to hunger. It has the tendency of environmental pollution and destruction of water bodies; it is the greatest threat to the country, livelihood of the rural communities and Agriculture in general.

The practice of sand winning is carried out at Kyekyewere which mostly affected about 15 rice farmers whose fields have been degraded

      - Bush Fire

Bush fire post the greatest threat and is responsible for the devastation of biodiversity particularly livestock and crops. The advent of the fourth quarter comes with its attendant rampant fires with great damages to Agriculture production since vast stretches of farmland as well as farm produce could be destroyed through wild bushfires. However, in our effort to minimize the incidence of bush fire, extensive campaign, fora, sensitization and education was embarked for farmers across the Municipality. This has resulted in the recording of no such incidence at the time of this report compilation.

      - Poor Road network

Poor road network has been a great hindrance to Agriculture production in the municipality. It is estimated that about 45 percent of communities are inaccessible and another 30 percent of roads in the Municipality are unmotorable during certain times of the year. The resultant effect is high postharvest loss since most Agricultural commodities can’t get to the market hence proned to spoilage and suffer deterioration in physical state.

      - Price variation of inputs

Currently the market price of inputs is exhibiting great volatility with constant increase in input prices every week creating massive instability in the local markets. Farmers complained of unstable and erratic price that wipes off their profits a situation they claimed impacts negatively on their business hence affecting their standard of living.

      - Pest & diseases

Major pest identified during the quarter includes; Fall Army worm, Aphids, Mealy bug of cocoa, tomato fruit borer, Army worm beetle, diamond back moth of cabbage and white flies.  However, it must be noted that only the diamond back moth of cabbage was of significant importance due to its resistance to pesticides used to control it, the others were controlled effectively.

      - Quantity of Chemicals Distributed under FAW

Table 4.7.1 Quantity of chemicals distributed

| DISTRICT | Type of Chemical | Quantity of chemical received | Quantity of Chemical Distributed | Unit of measure |  | Beneficiary farmers |  | Coverage (Ha) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Litres | (Kg) | M | F |  |
|  | Viper | 9.6 | 9.6 | Litres |  | 29 | 12 | 39.99 |
|  | Bio T. Plus | 8700 g | 8700 g | (Kg) |  | 55 | 20 | 54.37 |

Source: A total of 116 farmers benefited from 9.6 litres of Viper and 8700gramme of Bio T Plus to spray 94.36 hectares of farm during the period under review.

      - Number of Agro-input outlets in the region

Table: 4.7.2. Number of Agro-input retail outlets in the District

| DISTRICTR | Number of registered input dealers |  | Number of unregistered input dealers |  | Total |  | Number of input outlets and sale points of which both registered and unregistered |  |  |  |  |  |  |  | Number of Districts Without Input outlet/sale points |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Solely Crop input |  | Solely Livestock input |  | Solely Fisheries input |  | Mixed Input Outlet |  |  |  |
|  | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 |
|  | 2 | 23 | 25 | 27 | 27 | 27 | 27 | 2 | 2 | 2 | - | - | 27 | 27 |  |  |

ANALYSIS: Two (2) new Agrochemical shop have been registered in addition to the existing ones bringing to 27 the total number both registered or unregistered shops in the Municipality. Quality service delivery is yet to be achieved as most of them are not well trained with a few of them operating under substandard conditions.

4.7.1.15 Enhanced Farmers' Access to Improved Technology

Access to Improved Agriculture Technology and Extension Services

Table 4.7.3 Access to Agriculture Technology and Extension Services

| Indicator |  | Target | 2021 | 2022 |
| --- | --- | --- | --- | --- |
| - Number of improved Technology demonstrated to farmers: | Livestock |  |  | 1 |
|  | Fisheries |  |  | - |
|  | Crop |  |  | 23 |
|  | Others |  |  | - |
| Area (acres)under improved Technology demonstrated to farmers: | Livestock |  |  | 1 |
|  | Fisheries |  |  | - |
|  | Crop |  |  | 6 |
| - Extension Agent-farmer ratio |  | 1:500 | 1:5,458 | 1:7,277 |
| - Total number of farmers participating in demonstrations | M |  | 700 | 1,115 |
|  | F |  | 300 | 473 |
| - Number of FBOs trained in extension services delivery |  |  | 5 | 4 |

ANALYSIS: The current Extension Agent-farmer ratio as at the time of this report compilation stands at 1:7,277 as against the same period the preceding year of 1:5,458. Comparing this to the standard ratio falls far below the FAO recommended ratio of 1:500. The implications are that extension of improved technologies by AEAs to majority of farmers in more remote communities will be hampered.

4.7.1.16. Farmer Based Organizations

| Type of FBOs | 2021 |  | 2022 |  |
| --- | --- | --- | --- | --- |
|  | M | F | M | F |
| Crop | 346 | 165 | 1,497 | 1,344 |

ANALYSIS: The number of existing functional FBOs in the municipality stood at 2,841during the same period the preceding year membership of FBOs stood at 511 with breakdown of 165 F and 346 M.

4.7.1.17 Agricultural Extension Service Performance

Table 4.7.5 Availability of Agricultural Extension Services

| MMDA | 2021 |  |  | 2022 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | M | F | Total | M | F | Total |
| Number of AEAs required |  |  | 32 |  |  | 32 |
| Number of AEAs at post | 8 | 1 | 9 | 8 | 1 | 9 |
| % AEAs at post compared to required |  |  | 28% |  |  | 28% |
| % of F AEAs at post |  | 11% | 18% |  | 11% | 18% |
| Number of farmers | 62,200 | 3,300 | 65,500 | 62,200 | 3,300 | 65,500 |
| Ratio of farmer to AEAs at post |  |  | 1:7,277 |  |  | 1:7,277 |

ANALYSIS: The total number of AEAs at post is 9 and same for same period preceding quarter. Comparing this against the required number of 32 translate into a deficit of 37.5%. Some AEAs have retired hence the need for replacement to augment the staff strength so as to ensure effective and enhanced service delivery for greater productivity.

4.7.1.18 Demonstrations conducted

Table 4.7.6 Number and types of demonstration conducted

| DIST | No. of Demonstrations conducted |  | Type of demonstration |  | Beneficiaries |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M |  | F |  |  |
|  | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 |  |
|  | 2 |  | Maize & Cowpea intercrop |  | 43 |  | 21 |  |  |
|  |  |  | GAPs Rice demo. |  | 376 |  | 104 |  |  |
|  |  | 23 |  |  |  | 1,155 |  | 473 | 1,728 |

ANALYSIS:  A total of 23 demonstrations were conducted during the period under review with beneficiaries of 1,728. During the same period the preceding year two (2) demonstrations were conducted with 544 farmers participating. Types of demonstrations conducted are: Maize Cowpea intercrop, GAPs in Rice production which entails the following:-System of rice intensification, Row planting, Nutrient Management, Bond construction in rice production and Row planting.

      - Improved Technologies Adopted by Farmers

Table 4.7.7 Farmers adopting improved technologies

| No. | Type of Technology adopted |  | M |  | F |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 |
| 1. | Row planting |  | 264 |  | 85 |  |
| 2. | Zero tillage |  | 215 |  | 85 |  |
| 3. | Recommended land development in rice production |  | 235 |  | 57 |  |

ANALYSIS: During the same period the preceding quarter a total of 941 farmers adopted technologies introduced to them and among them are: row planting, zero tillage, land development in rice production. This will result in increased production and yield respectively

      - Extension home and farm visit

Table 4.7.8 Number of extension home and farm visits conducted.

| DISTRICT | Total number of farmers visited | 2021 |  | Total number of farmers visited | 2022 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | M | F |  | M | F |
|  | 14,808 | 9,866 | 4,942 | 8,790 | 6,401 | 2,389 |

ANALYSIS: AEAs conducted 395 home and farm visits and reached out to 8,790 farmers comprising 8,790Ms and 2,389Fs. However, during the same period the preceding year AEAs conducted 458 home and farm visits and reached out to 14,808 farmers comprising 9,866 Ms and 4,942 Fs. Key among activities conducted during AEAs home and farm visits were: Fora on bush fire prevention and control, Farmers trainings, Field Days, Education of farmers, fora on fall armyworm prevention and control, sensitization on PFJ.

      - Agricultural Mechanisation

Table 4.7.9 Availability of Agricultural Mechanisation

| Indicator |  | 2021 |  |  | 2022 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Actual | Target | Actual | Target | Actual |
| - Number of functional agricultural mechanisation service centres | New |  |  |  |  |  |
|  | Existing |  |  |  |  |  |
|  | Number of farmers having access to mechanised services | M | 1,500 | 650 | 2,000 | 0 |
|  |  | F |  | 250 |  | 0 |
| - Area ploughed |  |  |  | 90(HA) |  | 0 |
| Total number of trainees in the proper use and handling of farm machinery | tractor owners, operators, mechanics trained |  |  |  |  | Nil |

ANALYSIS: During the same period the preceding year a total of 90 hectares of land were ploughed for cultivation of rice and maize at Abonsuaso, Manfo, Tepa and Odikro Nkwanta. Services rendered to farmers included ploughing of land, planting of rice, harvesting of rice and threshing. In the current quarter no such activity was conducted due to the breakdown of the tractor and power tiller. The impact of the service provided enhance the gradual transformation from subsistence farming by farmers to commercialisation which will eventually lead to increased production, improved standard of living and poverty reduction.

However, no farmers were trained for handling of farm machinery during the period under review.

Table 4.7.10 Farmers’ Access to Improved livestock production Technology

| LIVESTOCK TECHNOLOGIES DEMONSTRATED | M | F | Total | % F |
| --- | --- | --- | --- | --- |
| Routine husbandry practices | 35 | 12 | 47 | 30 |
| Supplementary feeding in livestock/Mineral provision e.g. salt lick | 18 | 9 | 27 | 33 |
| Improved housing for small ruminants | 8 | 15 | 23 | 65 |
| T0TAL | 61 | 36 | 97 | 37 |

ANALYSIS: During the period under review three (3) technologies were demonstrated to farmers. Total beneficiaries for the technologies were 97 and this comprised 61 M and 36 Fs.

      - Farmers adopting improved livestock technologies adopted

Table 4.7.11 Farmers adopting improved livestock technologies

| No. | Number of Technologies adopted |  | M |  | F |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2021 | 2022 | 2021 | 2022 | 2021 | 2022 |
|  | 4 | 3 | 65 | 61 | 41 | 36 |

ANALYSIS: A total of three (3) livestock technologies were adopted by 97 farmers comprising 61 Ms and 36 Fs. Some technologies adopted include: Improved housing for small ruminants, Supplementary feeding in livestock/Mineral provision e.g. salt lick.

      - Enhanced Land and Environment Management

Climate change awareness and sensitization

Table: 4.7.12 Climate change awareness/sensitization Training

| Activities | Number of Trainings | Beneficiaries |  | Total |
| --- | --- | --- | --- | --- |
|  |  | M | F |  |
| *Catchment areas protection schemes (e.g. reclamation of arable land, re-afforestation, etc.) |  |  |  |  |
| Bush fire mitigation awareness/trainings | 18 | 1,850 | 920 | 2,770 |
| Overgrazing awareness and training sessions |  |  |  |  |
| Cropping management (e.g. Crop rotation, cover cropping etc.) | 9 | 1,334 | 550 | 1,884 |
| Water use management (e.g. bunding in rice fields, Drainage construction in flooded fields, Irrigation etc.) | 18 | 1,653 | 795 | 2,448 |
| Perennial fruits and fodder plantation against soil erosion | 2 | 18 | 8 | 26 |
| Integrated Pest Management (IPM) | 18 | 825 | 413 | 821 |
| Others … | - | - | - | - |
| TOTAL | 65 | 5,680 | 2,686 | 8,366 |

ANALYSIS: Climate change has been the most topical issue currently impacting negatively on crop production. The Impact is adversely felt on the environment with its associated effect on drying up water bodies, declining rainfall and gradual loss of biodiversity. In view of these sensitisation, education and training sessions was conducted for farmers on water use efficiency and management, cropping management and IPM.

Sixty five (65) sensitisations, fora, education and training sessions were conducted for farmers to enable them conserve the natural resources and water bodies. A total of 8,366 farmers comprising 5,680 Ms and 2,686 F participated.

      - Conservation Agriculture Demonstrations

Table 4.7.13 Conservation Agriculture demonstration

| Conservation System | Target Number of Demonstrations | Actual Number of demonstrations | Beneficiaries |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Total | M | F |
| Crop rotation | 9 | 1 | 13 | 8 | 5 |
| Mulching | 9 | 5 | 23 | 15 | 8 |
| Zero tillage | 9 | 5 | 30 | 20 | 10 |
| Cover cropping | 9 | 2 | 8 | 5 | 3 |
| Intercropping | 9 | 2 | 53 | 35 | 18 |

ANALYSIS:Demonstrations were conducted in selected communities across the Municipality notable among them includes: Tepa Bepokorkor, Jacobu, Pobiso, Manfo, Subriso, Numasua among others

      - Adoption of Conservation farming Systems

Table 4.7.14 Conservation Systems Adopted

| Systems | Types of Crops | Beneficiaries |  | Total | Number Adopted |  | Total | Percentage Adoption |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | M | F |  | M | F |  |  |
| Crop rotation | Cabbage/Garden egg | 850 | 35 | 885 | 850 | 35 | 885 | 100 |
| Mulching | Tomato | 15 | 8 | 23 | 15 | 8 | 23 | 100 |
| Zero tillage | Maize | 20 | 10 | 30 | 20 | 10 | 30 | 100 |
| Cover cropping |  |  |  |  |  |  |  |  |
| Intercropping | Cassava/Plantain | 35 | 18 | 53 | 35 | 18 | 53 | 100 |
| Others |  |  |  |  |  |  |  |  |

ANALYSIS: Over all adoption of conservation farming systems stood at 100% an indication that  adopting of technology extended to farmers is on the rise and this will in the long run enhance Agricultural productivity in the face of global climate change

4.7.1.26 Environmental Management

Table 4.7.15 Awareness/Sensitization on Environmental Management

| Item | Target Participants | Number of trainings | Beneficiaries |  | Total |
| --- | --- | --- | --- | --- | --- |
|  |  |  | M | F |  |
| Buffer observation | Vegetable growers | 9 | 97 | 25 | 122 |
| Illegal Mining | Cocoa farmers | 9 | 85 | 15 | 100 |
| Water Pollution | Vegetable growers | 9 | 40 | 25 | 65 |
| Sand winning | Rice farmers | 9 | 65 | 12 | 77 |

ANALYSIS:

Education, fora, sensitization, and awareness creation was organised for farmers across the municipality notable among the communities visited were: Kyekyewere, Achawkrom, Camp II, Mfante, Subriso, Mabang, Akwasiase, Yawtabrikrom, Betiako, Manfo, Asuhyiae, Achina, Jacobu, Dwaaho, and Odikronkwanta. Discussions focused on dangers and consequences of illegal mining on farming, the pollution of water bodies, the need for buffer observation and the threats posed by sand wining to crop production.

4.7.1.27 Results

Farmers gradually embracing the concept of the environment belonging to them hence embarking on preventive measures such as formation of watch dog committee to oversee and monitor waters bodies and its surroundings.

## BUSINESS ADVISORY CENTRE

### 4.8.1. Activities Planned for the Year

The following activities were planned for the quarter under review.

| No. | ACTIVITY | TARGET GROUP | VENUE | NO. OF PARTS. | FUNDING SOURCE | REMARKS |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Internship | Artisans | Kumasi | 5 | REP |  |
| 2 | Group Dynamics and Entrepreneurship | VSLO & Enterprise Group | Kwaku Dua krom , Gyamerakrom | 80 | Mondelez International |  |
| 3 | Entrepreneurship development training (2) | Graduate A apprentices | Tepa Municipal Assembly Hall | 80 | GOG |  |
| 4 | Business Counseling | SMEs/ Clients | District wide | 250 | GOG |  |
| 5 | NVTI Proficiency Exams | Final Year apprentices | Tepa Community centre | 230 | Master Card Foundation |  |
| 6 | Basic Kaizen training | Skill Craft Persons (SCPs) | Tepa Community Center | 33 | Master Card Foundation |  |
| 7 | Financial Management Training | REDF Applicants | Tepa | 85 | Tepaman Rural bank Limited |  |
| 8 | MBA training in basic KAIZEN | Women entrepreneurs | Tepa | 30 | Mastercard Foundation |  |
| 9 | Business forum on tax compliance | MSMEs within the municipality | Municipal Assembly Hall | 80 | AAMA |  |
| 10 | Facilitate MSMEs access to credit | MSMEs | Municipal Wide | 200 | REP |  |
| 11 | Conduct Training in business management | Artisans | Tepa | 80 | GOG |  |
| 12 | Facilitation in digitization for selected MSMEs | MSMEs | Tepa | 40 | GEA/ Master Card Foundation |  |
| 13 | Conduct Regulatory Requirement training for MSMEs | MSMEs | Tepa | 40 | GOG |  |
| 14 | Sensitization on You Start | The youth between 18-40 | Tepa & the surrounding villages | 450 | GEA |  |
| 15 | Entrepreneurship development training | Final Year Apprentice in dressmaking –GNTDA- Zone one | Tepa community centre | 75 | LBA |  |
| 16 | Business Counseling | SMEs/ Clients | District wide | 50 | REP |  |
| 17 | Internship training | SMEs/ Clients | Kumasi technical School | 5 | REP |  |
| 18 | Business Formularization | SMEs/ Clients | District wide | 40 | REP |  |
| 19 | Kaizen on the job training | O B Pakyiman ltd & Philipa’s vocational Centre | Pakyi & Suame | 45 | JICA |  |

    - Activities Implemented for the Year

      - Training

The BAC was able to implement the following programs during the quarter under review: (1) The Business Advisory Center organized training in basic kaizen for the 33 SCPs under A2E Component in the YAW Project. They were made up of 5 Ms and 28 Fs (2) Business counselling was conducted for two hundred and fifty (250) selected clients, (3) Financial Management training was also organized for fifty (50) selected SMEs. (4) In another development, one hundred and ninety three (193) final year apprentices were registered for the NVTI Proficiency exams. The table below shows the details of the implemented activities: However, the entrepreneurship development training for A2E grandaunts could not come on due to unavailability of funds for such activities

(5) A basic kaizen trainings were organized for the 16 employees at Joy Spring Ltd and Hill Bill Ltd. They were made up of 8 Ms and 10 Fs (6) Entrepreneurship and Group Dynamics training was conducted for Village Saving and Loan Organizations and Enterprise Groups in Four (4) communities which contributed to eighty (80) participants. They were made up of 71Ms and 51Fs respectively. (7) Entrepreneurship Development training was also organized for Forty (40) final year apprentice. (8) In another development, selected fifty SMEs were undertaken business counseling within the quarter under reviewed. The table below shows the details of the implemented activities

The following programs were implemented during the year under review: (9) Sensitization activities on Ghana Economic transformation Project GETP (10). Entrepreneurship Development training was also organized for Forty (47) final year apprentices at Anyinasuso.

(11) Sensitization activities on You Start and Ghana Job & Skills Project (GJSP) (12)   Entrepreneurship Development training was also organized for eighty six (86) final year apprentices belonging to GNTDA Zone One Made up of two Ms and eighty four (84) Fs . (13 Again kaizen on the job training was conducted for Philippa’s Vocational training center and OB Pakyiman Ltd. (5) Monitoring activities on SMEs which received Ghana enterprises transformation Project grant (GETP)

The table 4.8.1 below shows the details of the implemented activities during the year under review:

| DATE | ACTIVITY | TARGET GROUP | VENUE | NO. OF PARTS. |  |  | FUNDING SOURCE | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | M | F | T |  |  |
| 8th Feb 2022 | Training in Basic Kaizen | Skill Craft Persons (SCPs) | Tepa Community Centre | 5 | 28 | 33 | Master Card Foundation | The training was successfully conducted |
| 16th Feb, 2022 | Financial Management | Selected SMEs | Municipal assembly hall | 12 | 38 | 50 | Tepaman rural bank | The training was successful |
| 24th Jan- 10th December 2022 | Business counselling | SMEs | District wide | 66 | 184 | 250 | GOG | The counselling exercise was done successful |
| 17th Jan – 21st March 2022 | NVTI Proficiency Exams | Final Year Apprentices | Tepa Community | 18 | 212 | 230 | GOG/ Master card Foundation | Ongoing |
| 1st May- 30th June, 2022 | Training in Basic Kaizen | Joy Spring Ltd & Hill Bill Lte | Accra | 8 | 10 | 18 | JICA | The training was successfully conducted |
| 12th-19th April, 2022 | Group Dynamic Entrepreneurship Training | VSLO & Enterprise Group | Addaikrom Kwakuduakrom Gyamerakrom Hiamankwa | 71 | 51 | 122 | Mondelez | The training was successful |
| 24th -25th June, 2022 | Entrepreneurship Development Training | Final Year Apprentices | Tepa Community | 2 | 81 | 83 | LBA | The training was successful |
| 18th August-15th September, 2022 | Sensitization Programme on GETP | SMEs | Tepa & surrounding towns and villages | 126 | 255 | 381 | GEA | The programme was sucesssful |
| 8th -9th August 2022 | Entrepreneurship Development Training | Final Year Apprentices | Anyiasuso | 15 | 31 | 46 | LBA | The training was successful |
| 15th September-15th November, 2022 | Sensitization Programme on You Start & GJSP | Youth between 18-40 years | Tepa & surrounding towns and villages | 225 | 355 | 580 | GEA | The programme was sucesssful |
| 15th – 17th November, 2022 | Monitoring activities on Ghana Enterprises Transformation Project ( GETP) | SMEs/ Clients | Ayeduase & Ahodwo Kumasi | 1 | 1 | 2 | GEA/GETP | The monitoring was successful |
| 24th -25th November, 2022 | Entrepreneurship Development Training | Final Year Apprentices in GNTDA Zone one | Tepa Community Centre | 2 | 84 | 86 | LBA | The training was successful |
| 9th -23rd November, 2022 | Kaizen on the job project (OJT) | OB Pakyiman Ltd & Philippa’s Vocational Training Centre | Pakyi and Suame | 1 | 2 | 2 | JICA | The training was successful done |

Table 4.8. 2 Advisory, Counselling and Extension Services

| Service Areas | No. of Sessions | M | F | Total |
| --- | --- | --- | --- | --- |
| Financial Assistance | 16 | 67 | 117 | 184 |
| Business Start-up | 1 | 3 | 2 | 5 |
| Registration with RGD | 16 | 20 | 24 | 44 |
| Registration with NBSSI | 23 | 24 | 24 | 48 |
| Registration with GSA/FDA | - | - | - | - |
| Marketing of Products | 10 | 6 | 20 | 26 |
| Training Programs | 8 | 104 | 223 | 327 |
| Others (Please specify) | - | - | - | - |
| TOTAL | 74 | 224 | 410 | 634 |

Table 4.8.3 Summary of Activities Implemented

| Training Activities | No of Act. | M | F | Total |
| --- | --- | --- | --- | --- |
| Leadership Training/Group Dynamics | 4 | 71 | 51 | 122 |
| - Other (LBA) | 4 | 19 | 196 | 215 |
| - Other (JICA) | 1 | 8 | 10 | 18 |
| - NBSSI/MCF/YAW | 1 | 5 | 28 | 33 |
| - Other (JICA) | 1 | 8 | 10 | 18 |
| - NBSSI/MCF/YAW | 8 | 84 | 268 | 352 |
| - Other (Individual Client own effort) | 11 | 14 | 26 | 40 |
| - NBSSI/MCF/YAW | 1 | 11 | 28 | 49 |
| - Counselling & Extension Services | 4 | 66 | 134 | 200 |
| - Advisory (Provision of Information) | 74 | 224 | 410 | 634 |
| - Enterprise Site Inspection |  |  |  |  |
| - NVTI Exams | 3 | 18 | 212 | 230 |

4.8.2.2. Facilitating MSME Access to Credit

During the period under review, a total of 167 persons/client made up of 53 Ms and 114. Fs were assisted to access credit totaling GH¢ 674,900.00

Table 4.8.4 below provides details of MSE access to credit.

| DESCRIPTION/ITEM | NO OF BENEFICIARIES |  |  | AMOUNT GRANTED(¢) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | M | F | TOTAL | M | F | TOTAL |
| REDF | 30 | 85 | 115 | 190,800.00 | 381,800.00 | 572,600.00 |
| Matching Grant |  |  |  |  |  |  |
| MP’s Common Fund |  |  |  |  |  |  |
| Others (Specify) |  |  |  |  |  |  |
| Total | 30 | 85 | 115 | 190,800.00 | 381,800.00 | 572,600.00 |

4.8.2.3	Outcome of BAC activities for the Year

Table 4.8.5 Summary of Outcome

| OUTCOME | M | F | Total |
| --- | --- | --- | --- |
| Businesses Adopting New technology | 12 | 6 | 18 |
| Businesses Adopting Improved Technology | 7 | 5 | 12 |
| New Jobs Created | 42 | 64 | 106 |
| New Business Established | 26 | 48 | 74 |
| Businesses Diversifying Product | 5 | 7 | 11 |
| Businesses Diversifying Business | 4 | 5 | 9 |
| Businesses Adopting Improved Packaging | 1 | 14 | 15 |
| Businesses Recording Increasing Sales | 2 | 1 | 3 |
| Businesses Keeping Business Records | 12 | 17 | 29 |
| Businesses Selling Outside Home District | 5 | 9 | 14 |
| Businesses Having Access to MSME Information | 23 | 24 | 47 |
| Businesses Operating Active Bank Accounts | 6 | 7 | 13 |
| Businesses Supplying Products to Larger Enterprises | - | - | - |
| Businesses adopting good workshop safety and environmental management practices | 11 | 5 | 16 |
| Businesses with Improved Product Quality | 8 | 9 | 17 |
| Businesses with improved Management Practices | 1 | 2 | 3 |
| Businesses registered/contributing to SSNIT |  |  |  |
| Businesses Accessing New Markets | 6 | 10 | 16 |
| Businesses Recording Increased Production | 1 | 1 | 2 |
| Businesses with good credit management and improved loan repayment | 26 | 78 | 104 |
| Businesses employing good customer relations | 3 | 11 | 14 |
| Businesses that have Accessed Institutional Credit | 53 | 114 | 167 |
| Women Owned Businesses that have Access to Institutional Credit | - | 114 | 114 |
| Businesses Adopting Occupational Safety Health and Environmental Management | 11 | 7 | 18 |
| LTAs with improved leadership | 3 | 2 | 5 |
| LTAs networking with others |  |  |  |
| Businesses Recording Increased Profit | 5 | 5 | 10 |

4.8.2.4. No Training Funds Was Received from other Projects/Programmes/Institutions and Persons

E.g. REP, Municipal and District Assemblies, MP’s Common Fund, JICA, NGOs, etc. Please, state the exact amount received for programs during the period

| No. | Organization | Amount Released to the BAC for programs (GH¢) |
| --- | --- | --- |
| 2 | GOG | 1600.00 |

Funds Generated Internally

| NO. | TYPE OF ACTIVITY | AMOUNT GENERATED |
| --- | --- | --- |
| 1. | NBSSI Clients’ Registration | 700 |

4.8.2.5 Transfers to Regional Secretariat/Head Office/REP

An am amount of seven hundred Ghana cedis being NBSSI clients’ Registration, commitment fees, sale of products from technical training programmes, GSA Recommendation Letters was transfered to the regional secretariat/ head office during the quarter under review

| No. | Item | Amount transferred (Gh¢) |
| --- | --- | --- |
| 1. | NBSSI Clients’ Registration | 700 |

      - Networking/ Collaboration with other Institutions

No network with partner institutions, projects and programmes by BAC. Give detailed explanation on the nature of any on- going collaborations between the BAC and each partner institution/ projects/programmes.

  - GHANA AMBULANCE SERVICE

### 4.9.1. Emergencies attended within the Year 2022

Table 4.9.1 shows recorded cases within the year 2022

| Months | Cases Attended |
| --- | --- |
| January | 18 |
| February | 6 |
| March | 10 |
| April | 16 |
| May | 16 |
| June | 19 |
| July | 15 |
| August | 14 |
| September | 13 |
| October | 13 |
| November | 13 |
| December | 12 |
| Total number of Cases attended – | 165 |

    - Distribution of Cases attended under Age And Sex

Table 4.9.2: Distribution of cases attended under age and sex categories

| AGE GROUP | JAN |  | FEB |  | MARCH |  | APRIL |  | MAY |  | JUNE |  | JULY |  | AUGUST |  | SEPT |  | OCT |  | NOV |  | DEC |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | F | M | F | M | F | M | F | M | F | M | F | M | F | M | F | M | F | M | F | M | F | M | F |  |
| Less than | - | 1 | - | - | 1 | - | 1 | 3 | 3 | 2 | 1 | - | 1 | - | 1 | 2 | - | 2 | 1 | - | 1 | - | - | 2 | 22 |
| 1 – 14 | 2 | - | 1 | - | - | - | - | - | - | 1 | - | 2 | 1 | 2 | - | 1 | - | 1 | 1 | 1 | 1 | 1 | 1 | - | 16 |
| 15 – 29 | 3 | 4 | - | 2 | 3 | 4 | - | 4 | - | 4 | 1 | 5 | 1 | 3 | - | 2 | 2 | - | 1 | 2 | 1 | 1 | 5 | - | 48 |
| 30 – 44 | 1 | 2 | 1 | - | 1 | - | - | 2 | 3 | 1 | 1 | 1 | - | 1 | 2 | - | 4 | - | 1 | - | - | 1 | 2 | - | 24 |
| 45 – 59 | 3 | 1 | 2 | - | - | - | 4 | - | 1 | 1 | 1 | 1 | - | 3 | 1 | - | - | - | 1 | - | - | 1 | 1 | - | 21 |
| 60 & Above | - | 1 | - | - | 1 | - | - | 2 | - | - | 2 | 4 | 1 | 2 | 1 | 4 | 2 | 2 | 1 | 4 | 2 | 4 | 1 | - | 34 |
| Not Stated | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |
| Total | 9 | 9 | 4 | 2 | 6 | 4 | 5 | 11 | 7 | 9 | 6 | 13 | 4 | 11 | 5 | 9 | 8 | 5 | 6 | 7 | 5 | 8 | 10 | 2 | 165 |

Table 4.9.2 and Table 4.9.1 show that the month of June recorded the higher number of case.

Table 4.9.2 shows that the age category 15 – 29 recorded the highest cases 48 out of 165 cases.

    - Classification of Cases by Chief Complain / Type Of Illness

Table 4.9.3: Classification of cases by chief complaint / type of illness

| CHIEF COMPLAIN / TYPE OF ILLNESS | JAN | FEB | MAR | APRIL | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Abrasion / Laceration / Fracture | 8 | 1 | 2 | 1 | 3 | 1 | 1 |  | 2 | 1 | 3 | 5 | 28 |
| Abdominal pain / Diarrhoea and Vomiting | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 5 | 2 | 4 | 3 | 29 |
| Abnormal behaviour | - | - | 1 | - | - | - | - | - | - | - | - | - | 1 |
| Cardiovascular / Respiration problem | 2 | 1 | 2 | 8 | 3 | 4 | 4 | 3 | 2 | 2 | 2 | 3 | 36 |
| Burns | - | - | - | - | - | - | - | - | - | - | - | - | - |
| Convulsion seizure | - | - | - | - | - | 1 | 1 | - | - | - | 1 | - | 3 |
| General body pain | - | - | 2 | 2 | 1 | 1 | - | 2 | - | 1 | - | - | 9 |
| General urine cases | - | - | - | - | - | - | - | - | - | - | - | 1 | 1 |
| Pregnancy complication | 6 | 2 | 1 | 3 | 3 | 6 | 3 | 3 | 2 | 1 | 3 |  | 33 |
| Others poison, jaundice etc | - | 1 | - | - | 3 | 5 | 5 | 3 | 2 | 6 | - | - | 25 |
| Total | 18 | 6 | 10 | 16 | 16 | 19 | 15 | 14 | 13 | 13 | 13 | 12 | 165 |

Table 4.9.4:  Medium of Call to the Station

| SOURCE OF CALD | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Walk in | 1 |  | 1 |  | 1 |  |  |  |  |  |  |  | 3 |
| Control | 15 | 6 | 9 | 15 | 12 | 19 | 15 | 14 | 12 | 9 | 13 | 8 | 147 |
| Hospital / Clinic |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Residence |  |  |  | 1 | 1 |  |  |  |  |  |  |  | 2 |
| Others |  |  | 1 | 1 |  |  |  |  |  | 3 |  | 1 | 6 |
| Total | 16 | 6 | 11 | 17 | 14 | 19 | 15 | 14 | 12 | 12 | 13 | 9 | 158 |

Table 4 shows that control (Dispatched Center) recorded the highest number of call received before responding to a case.

Table 4.9.5: Emergency and Non-Emergency Cases Attended

| CASE | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NONEMERGENCY | 1 |  | 2 | 1 | 2 |  |  | 1 | 2 | 2 | 2 | 2 | 15 |
| EMERGENCY | 17 | 6 | 8 | 15 | 14 | 19 | 15 | 13 | 11 | 11 | 11 | 10 | 150 |
| TOTAL | 18 | 6 | 10 | 16 | 16 | 19 | 15 | 14 | 13 | 13 | 13 | 12 | 165 |

Table 5: Shows 150 emergency cases and 15 as non-emergency.

Type of Incident

| INCIDENT | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trauma | 7 | 1 | 2 | 1 | 3 | - | 1 | 1 | 2 | 1 | 3 | 5 | 27 |
| OBS & Gynae | 6 | 2 | 2 | 3 | 3 | 6 | 3 | 3 | 2 | 1 | 3 | - | 34 |
| Medical | 4 | 3 | 4 | 11 | 8 | 11 | 11 | 9 | 7 | 9 | 5 | 5 | 87 |
| Investigation (Scan) | 1 | - | 2 | 1 | 2 | 2 | - | 1 | 2 | 2 | 2 | 2 | 17 |
| Others | - | - | - | - | - | - | - | - | - | - | - | - | - |
| TOTAL | 18 | 6 | 10 | 16 | 16 | 19 | 15 | 14 | 13 | 13 | 13 | 12 | 165 |

Total number of delivery in Ambulance   	- 	Nil

Total number of death in Ambulance		  - 	2 (Two)

Total number of mid trip  			  -	 Nil

Total number of missed trip  			 - 	3 (Three)

    - Cases Referred from Tepa Municipal Hospital to Sunyani Regional Hospital, Komfo Anokye Teaching Hospital (Kath) and Other Facility

- Tepa Municipal Hospital to Sunyani Regional Hospital 		 - 	62

- Tepa Municipal Hospital to Komfo Anokye Teaching Hospital 	-  	20

- Tepa Municipal Hospital to Kwadaso Hospital (Kumasi) 	- 	 1

- Tepa Municipal Hospital to Suntreso Hospital (Kumasi)		 - 	 1         TOTAL 			 - 	                      				 84

    - Names of Health Centers and Chip Compound Cases Transported within the Municipality

Akwasiase Health Center 	- 	Nil

Manfo Health Center 		- 	7

Twabidi Health Center 	-	16

Subriso Health Center		-	 Nil

Anyinasuso Health Center 	- 	Nil

Betiako Health Center 	-	 1

Numasua CHIP Compound  	- 	1

Tetekrom CHIP Compound 	- 	Nil

Katapei CHIP Compound  	- 	Nil

Abonsuaso CHIP Compound	- 	Nil

Krakosua CHIP Compound 	-	 Nil

Asuhyiae CHIP Compound	- 	Nil

The above shows that Twabidi Health Center recorded the highest number of case referred.

    - Cases Referred Outside Tepa Municipality To Other Receiving Facility

1.	 Mpasaaso Health Center to Mankranso Government Hospital	-	2

2. 	 Mpasaaso Health Center to Komfo Anokye Hospital	  	- 	1

3.	 Mankranso Government Hospital to KATH  			   - 	1

4.          Total Number of cases     					             - 	4

CASES TRANSPORTED FROM THE MUNICIPALITY TO FACILITY IN AHAFO REGION

| Refer | Receiving Facility | Total |
| --- | --- | --- |
| Tepa Municipal Hospital | Bechem Government Hospital | 2 |
| Tepa Municipal Hospital | St. Elizabeth Catholic Hospital (Hwediem) | 1 |
| Twabidi Health Center | St. Elizabeth Catholic Hospital | 2 |
| Numasua CHIP Compond | St. Elizabeth Catholic Hospital | 1 |
| Tepa Municipal Hospital | PISHGA Hospital Bechem | 2 |
| Tepa Municipal Hospital | Kenyase Hospital | 1 |
|  | TOTAL OF CASES | 6 |

SOURCE OF FUEL

| SOURCE | FUEL AMOUNT |
| --- | --- |
| MOH | GH¢ 20,977.00 |
| NON MOH | GH¢ 16,110.00 |
| TOTAL | GH¢ 37,087.00 |

DISTANCE COVERED   - 21273KM

## 4.10 NATIONAL DISASTER MANAGEMENT ORGANIZATION (NADMO)

### 4.10.1. Programmes & Project

The year 2022 witnessed several activities undertaken by Ahafo Ano North Municipal NADMO which included educational campaigns and visits.

    - Pre-Disaster Management Activities

4.10.2.1. Education on Covid 19

During the first, second, third and latter part of the fourth quarter, there was intensive education campaign on Covid 19. As the name suggest it is a viral pandemic which is ragging the whole world with its impact on humans regardless of race and age. This pandemic has not left any continent or country with its sting so there is the need to create much awareness campaign to avoid its spread and thereby relief the government of the high cost of its treatment and use the money to develop the country.

It is in light of this that the Ahafo Ano North NADMO on our part took it upon us to educate people in our various communities.  They were educated that it was a viral disease which is very dangerous.  Ways to protect them from this disease is to wear nose mask always, wash hands under running water, use of hand sanitizer, avoid large crowds and also keep a clean environment. Also get vaccinated when one contracted the disease or not.

The communities that got this education were Brodeεsua, Manfo, Tepa Beposo, Mabang, Asuhyiae, Twabidi, Subriso, Betiako, and Akwasiase. The campaign was done house to house basis, durbars, community engagement, Churches, mosques.

An adage says better prevent a disease than to cure it.  Records have it that, after malaria the next major cause of death is road accident.  It is against this background that the Ahafo Ano north Municipal NADMO as an agency which co-ordinates with government and non-governmental agencies that deals with disaster and its prevention conducted an education on road safety.

The purpose of the education was to sensitize the public about the devastations that road accidents bring, the causes of road accident and the avoidance of road accidents. This education on road safety was not only meant for only drivers but the public which included school children, passengers, pedestrians.   Road signs were also taught.

4.10.2.2. Pre-Flooding, Desilting and Clean Up Exercise

There was an intensive pre-flooding, desilting and clean up exercise through all the four quarters   in the Ahafo Ano North Municipality. This exercise was done in order to prevent disasters like flooding which is due to choked gutters, diseases such as Cholera, Diarrhea, and Dysentery.  Beneficiary communities were Akwasiase, Twabidi, Tepa Beposo, Tepa Ward 3, Dwaaho, and Tepa Ward 4

4.10.2.3 Hazard mapping

Hazard Mapping is a means of promoting Disaster combat in the communities. This exercise often gives NADMO Officers the opportunity to identify structures and buildings that are in dilapidated state for immediate attention and consideration to avert disaster in the future.

Some of the Hazards identified were dilapidated buildings, electricity poles, a big gully which serves as a death trap in the community. These structures must be demolished so as to avoid any disaster that may drain the country’s coffers.

Beneficiary communities include Akwasiase, Twabidi, Tepa Beposo.

    - Disaster Risk Reduction and Climate Change Adaption

Disaster risk reduction aims at preventing new, reducing existing disaster and managing residual risk, all of which contribute to the strengthening resilience and to achieve sustainable development.

During the year under review, the Ahafo Ano North Municipal Secretariat of NADMO took the mandate to educate people in the communities of the negative effects of cutting down trees without replacing them, the use of chemicals and bush burning. Community members were advised to plant more trees and practice afforestation. Members were educated on good cultural farming practices.

Means of disseminating the information were on house to house basis, the media via information centres, schools, food vendors. Some communities which benefited from this education were Twabidi, Akwasiase,

4.10.3.1 Disaster

There were in all ten (10) disaster cases recorded affecting One hundred and six  (106) persons  with estimated cost of damage of Eighty-Two Thousand, Four Hundred and Forty four thousand,  Ghana Cedis only (GH¢ 82,444.00) in the year under review.  In all, one (1) bush fire, five (5) rainstorms, two (2) domestic fires and one (1) flood.

## 4.11 National Commission For Civic Education (NCCE)

### 4.11.1. General Overview of Activities Undertaken

Based on the programme guide that was given to the district for the year 2022, the following activities were taken out:

- Education on environmental governance

- Education on peaceful coexistence

- Education SIM card re-registration

- Education of Affirmative Action (child rights) and parental duties

- Education on Article 22 (Spousal rights)

- Education on Intimate Partner Violence

- Engagement with Civic Education Clubs

- Education on Fundamental Human Rights

- Education on Political History and Constitution

- Education on National Security

- Education on COVID-19 and safety protocols

- Constitution Week celebration

- Constitution Quiz

- Education on duties of citizens

- Education on good governance and accountability

- Education on duties of the Member of Parliament

- Violence extremism

- Gender equality

- Right to information Act 2019

- Campaign on corruption

Table 4.11.1. Below shows the summary of the activities undertaken from first to fourth quarter of 2022

| Programmes projected for 1st to 4th quarter and programmes implemented in the year 2022 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Ion For 1st -4th Quarter | Programme | No. Of Activities Implemented |  |  |  | Total Activities Implemented | Strategies/ Target | Beneficiaries |  |  |
|  |  | 1st Quart | 2nd Quart | 3rd Quart | 4th Quart |  |  | M(s) | F(s) | Total |
| 240 activities thus 60 per quarter | Education on environmental governance | - | 4 | 10 | 4 | 18 | Shops, group associations, markets | 77 | 222 | 299 |
|  | Peaceful coexistence | 6 | - | 10 | 2 | 18 | Shops, group associations | 105 | 178 | 283 |
|  | SIM card re-registration | 10 | - | 64 | - | 74 | General public, group associations, market place, community engagement, information center | 1,150 | 795 | 1,945 |
|  | Affirmative action child rights and parental duties | 2 | 1 | 4 | 1 | 9 | Shops, group associations, post-natal mothers | 802 | 914 | 1,716 |
|  |  |  |  |  |  |  |  | General Public |  |  |
|  | Article 22 (spousal rights) | - | - | 2 | - | 2 | Group associations | 20 | 49 | 69 |
|  | Intimate Partner Violence | - | 2 | 11 | - | 13 | Taxi ranks, shops, group association | 16 | 151 | 167 |
|  | Civic Education Clubs | - | - | 2 | 8 | 12 | Schools | 210 | 319 | 529 |
|  | Fundamental Human Rights | - | 2 | - | 4 | 6 | Taxi ranks, group associations, schools | 92 | 202 | 294 |
|  | Political history and constitution | 24 | 3 | - | - | 27 | Schools, radio, information centers | 840 | 740 | 1,580 |
|  |  |  |  |  |  |  |  | General Public |  |  |
|  | National security | - | 2 | - | - | 3 | Group associations | 57 | 202 | 259 |
|  | COVID-19 vaccines and safety protocols | 11 | 166 | - | 11 | 188 | Information centers, radio, communities | General Public |  |  |
|  | Constitution Week Celebration | - | 25 | - | - | 25 | Schools and radio | 650 | 600 | 1,250 |
|  | Constitution Quiz | - | 1 | - | - | 1 | Schools | 45 | 25 | 70 |
|  | Duties of citizens | 4 | - | - | - | 4 | Group associations, schools and radio | 500 | 300 | 800 |
|  |  |  |  |  |  |  |  | General Public |  |  |
|  | Good governance & accountability | 1 |  |  |  | 10 | Radio | General Public |  |  |
|  | Duties of Member of Parliament | 2 | - | - | - | 2 | Schools and Radio | General Public and estimated students of 500 |  |  |
|  | Violence extremism | - | - | - | 2 | 2 | Information centers | General Public |  |  |
|  | Gender equality | - | - | - | 6 | 6 | Churches, information centers, community engagement and shops | Estimated beneficiaries around 1,000 |  |  |
|  | Right to information Act 2019 |  |  |  | 4 | 4 | Information centers, Youth association, community engagement | Estimated beneficiaries 1,500 |  |  |
|  | Campaign on corruption |  |  |  | 3 | 3 | Group associations and Information center | Estimated beneficiaries 800 |  |  |
| Total | 20 | 60 | 206 | 103 | 45 | 427 | ************************* | ********************* |  |  |

    - Assessment of the Activities

The directorate commends the programs department for making a wise choice of activities that were carried out in the district, in accordance with the programs guide for the year 2022. Additionally, the directorate programme prediction for the year 2022 was Two Hundred and Forty (240). It is interesting to note that the Ahafo Ano North directorate of the Commission was able to fully implement 427activities. Through these initiatives, citizens at the three levels of practice—micro-individual, mezzo-group/association, and macro-community were made more knowledgeable about topics such as child protection, sound governance, specific provisions of Ghana's 1992 Constitution, environmental governance, and many others.

During the year under review, data was sorted for from some department such as the Municipal Education Directorate, Municipal Statistical Service, Tepa Traditional Council, Christian Council of Churches, Islamic community, the Municipal Assembly, the Municipal Ghana Police Service and departmental heads of government institutions in the municipality to help in the regional/district profiling requested by the commission that will aid in the effective and efficient civic education. Also, there was one (1) media coverage on the constitution week celebration which was done by MPUNTUO FM in the second quarter of 2022.

According to the Mobile Network Operator Agents in the municipality, the community's enhanced awareness of the SIM card re-registration increased the number of individuals who participated in the SIM Card biometric registration. Also, people who the directorate educated on Article 22 of Ghana's 1992 Constitution (spousal rights) expressed gratitude for the insightful education. Through this education, a widow in Tepa confided in the staff about her problems, and the directorate referred the widow to the Ahafo Ano North District Court Registrar so that the proper action could be conducted and as at December 2022, letters of administration has been granted to the widow.

Moreover, the awareness-raising about violence against women and girls cleared the path for many women to be aware of the appropriate municipal entity to report such situations to. Nevertheless, the directorate asked the Municipal Assembly for funding to aid in the planning of the Constitution Quiz Competition between four (4) Schools that is Wesley Methodist JHS, English Arabic ‘B’, CITA Educational Complex and Seventh Day Adventist JHS all in Tepa.

The directorate was able to collaborate with the Municipal Health Directorate educate almost all communities in the Ahafo Ano North municipality on COVID-19 safety protocols and its vaccines. This collaboration recorded the highest activity that was implemented in the year 2022 and it increased the turnout of citizens in taken the vaccination in the communities as reported by the Lead of the Municipal COVID-19 team. In addition, the directorate worked with COCOBOD Ahafo Ano North division to sensitized farmers and sprayers on parental duties and child rights.

From the aforementioned, it is obvious that the effort that the staff put in getting activities implemented in the year 2022 was encouraging and commendable as compared to the previous year 2021 which recorded Three Hundred and Forty-nine activities (349). In addition, through our public engagements to empower citizen by making them compliant to the constitutional provisions, most group associations, departments and schools in the Ahafo Ano North municipality appreciated the directorate’s work as an independent institution and some association made it clear to partner the directorate to organize programmes in the subsequent years.

## ENVIRONMENTAL HEALTH UNIT

### 4.12.1 Activities Carried Out

4.12.1.1 Evacuation of Refuse / Push and Levelling

To ensure clean and safe environment, evacuation of No. 4 refuse dumps at Tepa near Nursing Training School, Danyame, Anyinasuso and Akrofoso respectfully. Also normally push and levelling activities which normally done by waste landfill company limited on every quarterly was equally successfully done.

Below is the data that shows before and after work done

| S/N | DATE BEFORE | DATE AFTER | COMMUNITIES | REMARKS |
| --- | --- | --- | --- | --- |
| 1 | 10/03/22 | 30/03/22 | Anyinasuso | Successful |
| 2 | 10/03/22 | 30/03/22 | Danyame | Successful |
| 3 | - | 10/06/22 | Tepa near Nursing School | Successful |
| 4 | - | 24/08/22 | Akrofoso | Successful |

4.12.1.2 Desilting and Cleansing Of Drains At Central Business District (CBD), Town Centers And Other Public Spaces.

Several communities based clean up exercise and municipal wide desilting and clean- up exercise were organized by the Municipal Assembly as effort to improve sanitation and hygiene. The municipal wide exercise attracted a lot of support of the general public.

Below is the breakdown of the participation for the major municipal wide clean -up and desilting exercises.

| PARTICIAPNTS | GENDER | ATTENDANCE |
| --- | --- | --- |
| General Public | Male | 156 |
|  | Female | 93 |
| Zoomlion Ghana Ltd | Male | 13 |
|  | Female | 98 |
| Assembly Staff | Male | 17 |
|  | Female | 13 |
| Ghana Fire Service | Male | 9 |
|  | Female | 4 |
| Traditional Council & Assembly Members | Male | 11 |
|  | Female | 6 |
| TOTAL |  | 420 |

As always, the drivers and their mates who mostly create this waste refuse to support in cleaning the area and the EHSU took necessary actions against such recalcitrant offenders. Some logistics used were rooms, rakes, wheelbarrows, tricycles, shovels hand gloves and nose masks which were all provided by the Municipal Assembly.

4.12.1.3 Enforcement of Noise Control Regulation

The noise control sub-unit of EHSU continued to educate the public on the effects and dangerous associated to noise especially the noise emitters through information centres and community gathering.

Below are the details

| S/N | DATE | COMMUNITY | ATTENDANCE |  | REMARKS |
| --- | --- | --- | --- | --- | --- |
|  |  |  | MALE | FEMALE |  |
| 1 | 01-3-22 | Abonsuaso | 37 | 19 | Successful |
| 2 | 18-8-22 | Tepa Community Centre | 51 | 17 | Successful |
| 3 | 17-5-22 | Anyinasuso | 32 | 21 | Successful |

4.12.1.4 Sensitization on the Use of Iodized Salt.

On 10th - 12th May, 2022, the environmental Health of EHSU continued to carry out public health education in sensitizing the general public on the importance of iodized salt. The education was centered on the following key areas;

- Urging the public through education to partake the iodized salt as directed by FDA.

- Using iodized salt to avoid getting goiter infection / disease.

4.12.1.5 Food Hygiene and Safety:

The Assembly engages the services of KYB MEDICAL LABORATORY Service to do the medical screening for food and drink sellers in the municipality. A total number of one thousand and forty (1040) food and drink vendors were medically screened in the Municipality.

Out of the total number screen, 1026 were found fit and certificate were issued to them representing (95%) whilst 14 vendors were unfit to handle food for human consumption. They were advice to seek for medical treatment before they will be allowed to sell food to the general public.

4.12.1.6 Supervision And Monitoring Of Environmental Health Programmes

The environmental health officer supervises and monitoring the Assembly Labourers and the Zoomlion to ensure proper cleaning of the market, thorough fare and undertook daily collection of solid waste in Tepa Township to the final disposal site. They also supervise communal labour organize in some communities in the district.

4.12.1.7 Stray Animal

The EHSU embark on sensitivity the communities on how to keep their animals in their pound / pen. Since most of the communities are predominantly a farming community. These stray animals destroying farm produce and at times cause accident during road crossing. The community visited are Akwasiase information centre, Abonsuaso, Anyinasuso, Manfo etc.

4.12.1.8 Waste Management

Estimated Tonnage of Solid Waste Generated, Collected and Uncollected

The total estimated tonnage of SW generated during the second quarter of the year under review was tonnes

Table 1.0 Tabular representation of estimated tonnage of solid waste generated, collected and uncollected

| Solid Waste collected and uncollected | SW Percentage collected/uncollected | Per day collected/uncollected tonnage of SW | Estimated tonnage of SW collected/Uncollected |
| --- | --- | --- | --- |
| Collected and disposed | 86.31 % | 87.21 tons | 7,848,.90 tons |
| Uncollected (Burning, Burying, Indiscriminate disposal) | 13.69 % | 13.84 tons | 1,245.60 tons |
| Total tonnage of SW generated | 100% | 101.05 tons | 9,199.80 tons |

4.12.1.9 Premises Inspection

The ESHU continued to carry out their routine premises inspection as effort to improve hygiene and sanitation within the municipality. These included households, schools, eating premises, hospitality facilities, industries, warehouses, markets, lorry terminals, etc. A total of Three Thousand, six hundred and ninety-one premises (3,691) were inspected and nuisances detected were called for abatement.

The breakdown of the number of premises and common nuisances detected were as follows;

| No. | Premises | Total Number inspected | Common nuisances |
| --- | --- | --- | --- |
| 1 | Households | 3,531 | - Indiscriminate dumping of refuse elsewhere on premises. - Burning of refuse on premises - Connection of effluent into public drains. |
| 2 | Schools | 34 | - Indiscriminate dumping of refuse elsewhere on premises. |
| 3 | Eating premises | 56 | - General insanitary environment. |
| 4 | Hotel, Hostels, Guest houses and Motels | 11 | - Insanitary drains with algae growth on premises. |
| 5 | Industries, Warehouses | 29 | - General insanitary environment. - Accumulation of trade refuse on premises. |
| 6 | Lorry terminals | 3 | - Accumulation of refuse exposed to flies on bare ground. |
| 7 | Public toilets | 27 | - General Insanitary environment |
|  | TOTAL | 3,691 |  |

4.12.1.10 Law Enforcement

| Zonal council | Court Summons |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Total no. issued | Total no. complied with | Total no served | No. withdrawn | Bench warrant | Pending |
| Tepa | 507 | 452 | 15 | 9 | 3 | 3 |
| Kwasu Abu | 301 | 234 | 1 | 1 | 0 | 0 |
| Biokoye | 202 | 176 | 3 | 2 | 1 | 1 |
| Abu bone | 198 | 145 | 4 | 4 | 0 | 0 |
| Anyinasuso | 415 | 397 | 18 | 10 | 5 | 3 |
| Subriso | 519 | 503 | 16 | 11 | 3 | 2 |
| Suponso | 120 | 97 | 1 | 1 | 0 | 0 |
| Total | 2262 | 2004 | 58 | 38 | 12 | 9 |

# 5.0 APPENDIXES

## 5.1 Summary of Development Projects-Appendix I

| NO. | SECTOR | NO. OF PROJECTS | NO. ON-GOING | NO. COMPLETED | REMARKS |
| --- | --- | --- | --- | --- | --- |
|  | Education | 1 | 1 |  |  |
|  | Economic | 2 | 1 | 1 |  |
|  | Water / Sanitation | 1 | 1 |  |  |
|  | Health | 3 | 3 |  |  |
|  | Energy | - | - | - |  |
|  |  | - | - | - |  |

Source: Municipal Planning Coordinating Unit, 2022

## 5.2 Project List-Appendix 2

| PROJECT DESCRIPTION | DEVELOPMENT DIMENSION / THEMATIC AREA | LOCATION | CONTRACTOR/CONSULTANT | CONTRACT SUM (GHS) | SOURCE OF FUNDING | DATE OF AWARD | DATE STARTED | EXPECTED DATE OF COMPLETION | EXPENDITURE TO DATE | OUTSTANDING BALANCE | IMPLEMENTATION STATUS | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Construct and Furnish office for the Ghana Ambulance Service | Social Development | Tepa | M/S Runners Construction Works | 271,200.00 | DACF-RFG | 07/09/21 | 15/09/2021 | 14/12//2021 | 179,309.26 | 91,890.74 | 90% | On-going |
| Construction of Keniago CHPS Compound | Social Development | Keniago | 3M Enterprise | 170,000.00 | DDF | 05/06/18 | 05/12/18 | Not Completed | 165,418.70 | 4,581.30 | 70% | On-going |
| Construction of 1No. 6-Unit Classroom Block | Social Development | Odikro Nkwanta | Gomens Co. Ltd | 396,420.00 | DACF | 11/12/17 | 11/06/18 | Not Completed | 260,315.50 | 136,104.50 | 50% | On-going |
| Rehabilitate 3.5km Feeder Road at Okyerekrom | Environment, Infrastructure and Human Settlements | Okyerekrom-Sunorosuso | KIPO CONST. | 136,858.11 | GPSNP | 15/05/19 | 22/05/19 | 10/03/20 | 0.00 | 136,858.11 | 60% | Terminated |
| Drilling of 5 number boleholes | Social Development | Tepa Bonkrom Achina | Linzo Logistics | 86,000.00 | DACF | 14/10/22 | 17/10/22 | 17/11/22 | 86,000.00 | - | 100% Completed | Completed and in use |
| Rehabilitation of Circuit Court Judge’s residence | Governance, Corruption & Public Accountability | Tepa | Devada | 30,000.00 | DACF | 07/11/19 | 09/12/19 | 09/03/20 | 30,000.00 | 3,321.40 | 95% completed | On-going |
| Complete Zonal Council Office at Akwasiase | Governance, Corruption & Public Accountability | Akwasiase | Fiikan Co. Ltd | 199,142.24 | DACF | 16/06/22 | 18/07/22 | 18/08/2022 | 117,882.00 | 106,521.34 | 70% completed | On-going |
| Drilling and Installation of 3No.125mm Diameter Borehol | Social Development | ADUMSA Atobra Nyamebekyere | Ed Kanner | 117,882.00 | MPDACE | 16/06/22 | 18/07/22 | 118/08/2022 | 117,882.00 | - | 100% completed | Completed and in use |
| Construction of 2210m2 vibrated concrete at Tepa Market | Economic Development | Tepa | Messrs Fly Yee Ventures Ltd | 449,681.75 | DACF-RFG | 30/10/20 | 6/11/20 | 8/02/21 | 361,174.00 | 88,507.75 | 100% completed | Completed and in use |
| Construction of 1No. 20-Seater Water Closet at Tepa | Social Development | Tepa | M/S Runners Construction Works | 229,997.25 | DACF-RFG | 30/10/20 | 6/11/20 | 6/01/21 | 205,525.58 | 24,471.67 | 100% completed | Completed and in use |
| Construction of 1No. 10 unit lockable markets and 48 unit stalls at Tepa | Economic Development | Tepa | Messrs May Alab Ventures Ltd | 499,251.90 | DACF-RFG | 30/10/20 | 6/11/20 | 8/02/21 | 499,251.90 | 0.00 | 100% completed | Completed and in use |
| Construction of 60-Bed capacity Municipal Hospital | Social Dimension | Tepa | Contract award details not shared with the Municipal Assembly | Contract award details not shared with the Municipal Assembly | EUROGET | -Do- | -Do- | -Do- | -Do- | -Do- | 100% completed | Completed and in use |
| Construction of Jubilee Market | Economic Development | Tepa | Contract award details not shared with the Municipal Assembly | Contract award details not shared with the Municipal Assembly | MLGRD | -Do- | -Do- | -Do- | -Do- | -Do- |  | Standstill |

## 5.3 Financial Performance 2022–Ahafo Ano North Municipal Assembly-Appendix 3

| Source | 2021 |  | 2022 |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Approved Budget | Actual Expenditure |  | Approved Budget | Actual Expenditure |
| GOG | 2,154,843.35 | 2,704,857.13 |  | 2,201,048.84 | 3,184,893.31 |
| I.G. F | 648,000.00 | 560,667.80 |  | 848,000.00 | 693,942.05 |
| Donor Partners | 548,984.11 | 115,960.78 |  | 569,014.87 | 61,066.74 |
| CBRDP/CSWA | - | - |  | - | - |
| Common Fund | 4,688,897.75 | 1,073,476.17 |  | 5,057,610.85 | 2,254,269.45 |
| Others | - | - |  | - | - |
| HIPC | - | - |  | - | - |
| Retention Acct | - | - |  | - | - |
| DACF-RFG | 1,828,287.37 | 1,308,763.96 |  | 1,291,250.20 | 254,336.81 |
| U.N.D.P | - | - |  | - | - |
| TOTAL | 9,869,012.58 | 5,763,725.84 |  | 9,966,924.76 | 6,448,508.36 |

### 5.3.1. Revenue Mobilization – Appendix 4

| NO |  | 2020 |  |  | 2021 |  |  | 2022 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Revenue Head | Budgeted | Actual | Variance | Budgeted | Actual | Variance | Budgeted | Actual | Variance |
|  | Rates | 90,885.59 | 99,851.76 | (8,966.17) | 115,946.00 | 116,112.57 | (8,704.57) | 157,527.00 | 115,063.46 | 42,463.54 |
|  | Land | 189,342.31 | 109,898.00 | 79,444.31 | 191,594.00 | 135,180.00 | 17,443.83 | 430,013.00 | 234,679.40 | 195,333.60 |
|  | Fees | 110,335.57 | 176,356.07 | (66,020.50) | 1,555,414.00 | 101,530.49 | 22,854.10 | 160,514.00 | 120,943.07 | 39,570.93 |
|  | Licenses | 205,694.15 | 189,014.08 | 16,680.07 | 128,946.00 | 166,579.74 | 52,716.45 | 128,946.00 | 116,170.52 | 12,775.48 |
|  | Fines & Penalties | 60,000.00 | 31,157.00 | 28,843.00 | 11,000.00 | 10,070.00 | (683.33) | 11,000.00 | - | 11,000.00 |
|  | Rent | 60,000.00 | 240.00 | 59,760.00 | 45,000.00 | 39,899.43 | 5,250.00 | 45,000.00 | 48,646.25 | (3,646.25) |
|  | Grants | 12,945,408.95 | 6,035,597.43 | 4,236,129.40 | 9,221,012.40 | 5,516,108.87 | (157,605.24) | 911,924.76 | 6,641,678.43 | (5,729,753.67) |
|  | Miscellaneous | 20,808.00 | 19,302.48 | 1,505.52 | 110,000.00 | 8,258.68 | 101,741.32 | 15,000.00 | - | 15,000.00 |
|  | Total | 13,771,666.57 | 6,617,379.71 | 7,154,286.86 | 11,268,912.40 | 6,228,731.22 | (68,728.72) | 10,066,927.76 | 7,277,181.13 | (2,789,746.63) |

### 5.3.2 Expenditure – Appendix 5

| NO |  | 2020 |  |  | 2021 |  |  | 2022 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Revenue Head | Budgeted | Actual | Variance | Budgeted | Actual | Variance | Budgeted | Actual | Variance |
| 1. | Prson Emol. | 2,230,613.04 | 2,082,270.58 | 148,342.46 | 2,144,426.35 | 2,734,101.67 | (589,675.32) | 2,110,611.84 | 3,197,247.51 | (1,086,635.67) |
| 2. | T&T | 270,290.00 | 171,980.78 | 98,309.22 | 78,000 | 75,176.50 | (2,823.5) | 237,000.00 | 235,442.65 | (1,557.35) |
| 3. | Good & Services | 163,705.62 | 130,738.44 | 32,967.18 | 4,908,670.42 | 1,828,898.17 | 1,079,772.25 | 2,530,536.00 | 1,424,403.33 | 1,106,132.67 |
| 4. | Maintenance | 10,000.00 | 9,670.00 | 330.00 | 50,000.00 | 45,000.00 | 5,000.00 | 83,400.00 | 49,088.80 | 34,311.20 |
| 5. | Miscellaneous | 7,200.00 | 1,978.21 | 5,221.79 | 75,000.00 | 52,468.16 | 22,531.84 | - | - | - |
| 6. | Capital Exp. | 10,952,795.91 | 4,117,698.27 | 6,835,097.64 | 31,200.00 | 30,760.00 | 440.00 | 4,781,638.04 | 1,337,329.67 | 3,444,308,.37 |
| 7. | Utilities | 37,500.00 | 29,645.00 | 7,855.00 | 70,000.00 | 63,211.06 | 6,788.94 | 22,000.00 | 20,944.00 | 1,056.00 |
| 8. | Training | 99,562.00 | 50,945.20 | 48,616.80 | 70,000.00 | - | 70,000.00 | 201,638,88 | 183,999.40 | 17,639.48 |
| 9. | Special Service | - | - | - | - | - | - | - | - | - |
| 10 | Other Charges |  |  |  | - | 318.00 | (318.00) | 100.00 | 53.00 | 47.00 |
| 11 | Emergency | - | - | - | - | - | - | - | - | - |
|  | TOTAL | 13,771,667.19 | 6,594,926.48 | 7,176,740.71 | 7,357,296.77 | 6,136,197.84 | 659,618.32 | 9,966,924.76 | 6,448,508.36 | 3,518,416.40 |

## 5.4 Variance of Financial Performance- Appendix 6

| VARIANCE 2021 |  | VARIANCE 2022 |  | REMARKS |
| --- | --- | --- | --- | --- |
| ACTUAL RECEIPT | ACTUAL EXPENDITURE | ACTUAL RECEIPT | ACTUAL EXPENDITURE |  |
| 6,228,731.22 | 6,136,197.84 | 7,277,181.13 | 6,448,508.36 |  |

## 5.5 Way Forward

The thrust areas for the Assembly in the ensuing year include;

- Increase in revenue mobilization.

- Continuous Implementation of government flagship project.

-complete ongoing projects

-Build capacity of staff